{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["*****","01_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":15,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"*****","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"01_5YrWkPlan","index":1,"n_rows":1146,"n_cols":25,"rows_kept":1146,"cut":false,"hidden":false,"merged":[[312,1,312,2],[313,1,313,2],[254,1,254,2],[268,1,268,2],[269,1,269,2],[270,1,270,2],[271,1,271,2],[272,1,272,2],[273,1,273,2],[274,1,274,2],[308,1,308,2],[309,1,309,2],[310,1,310,2],[311,1,311,2],[304,1,304,2],[305,1,305,2],[306,1,306,2],[307,1,307,2],[300,1,300,2],[301,1,301,2],[302,1,302,2],[303,1,303,2],[296,1,296,2],[297,1,297,2],[298,1,298,2],[299,1,299,2],[292,1,292,2],[293,1,293,2],[294,1,294,2],[295,1,295,2],[288,1,288,2],[289,1,289,2],[290,1,290,2],[291,1,291,2],[284,1,284,2],[285,1,285,2],[286,1,286,2],[287,1,287,2],[280,1,280,2],[281,1,281,2],[282,1,282,2],[283,1,283,2],[276,1,276,2],[277,1,277,2],[278,1,278,2],[279,1,279,2],[251,1,251,2],[252,1,252,2],[253,1,253,2],[255,1,255,2],[256,1,256,2],[257,1,257,2],[258,1,258,2],[259,1,259,2],[275,1,275,2],[260,1,260,2],[261,1,261,2],[262,1,262,2],[263,1,263,2],[264,1,264,2],[265,1,265,2],[266,1,266,2],[267,1,267,2]],"flags":["formulas_cached_only"]}
[]
["DUVAL  SCHOOL DISTRICT - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["DUVAL   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted ",{"$nulls":8},"Last Revised",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format, as you received it (not a fax), prior to October 1, 2001, and all data accurate as of July 15, 2001.",{"$nulls":8},"2000-03-17",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"DUVAL","Date: ==>","2001-08-01",null,"For fiscal years","  2001-2002 through 2005-2006"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Seal exterior walls and caulk windows Building 86 C.","ARLINGTON ADMINISTRATION BLDG.",33000,{"$nulls":4},33000]
[null,"Electrical / Mechanical/Elevator upgrades","CENTRAL ADMINISTRATION BLDG.",1000000,{"$nulls":4},1000000]
[null,"Stage drapes.","DISTRICT WIDE",55000,55000,55000,55000,55000,275000]
[null,"Fencing.","DISTRICT WIDE",15000,15000,15000,15000,15000,75000]
[null,"Contingency for safety-to-life emergencies.","DISTRICT WIDE",100000,100000,100000,100000,100000,500000]
[null,"Electrical System Testing.","DISTRICT WIDE",25000,25000,25000,25000,25000,125000]
[null,"Bleacher repair.","DISTRICT WIDE",125000,125000,125000,125000,125000,625000]
[null,"L.P. Tank Relocate, Repipe and Fence.","DISTRICT WIDE",100000,100000,100000,100000,100000,500000]
[null,"Electrical upgrade for new wall heat pumps.","DISTRICT WIDE",515000,515000,515000,515000,515000,2575000]
[null,"Replace or repair HVAC.","DISTRICT WIDE",6315000,6315000,6315000,6315000,6315000,31575000]
[null,"Replace Fire Alarm and Intercom.","DISTRICT WIDE",389000,389000,389000,389000,389000,1945000]
[null,"Replace delaminating cabinets.","DISTRICT WIDE",1000000,1000000,1000000,1000000,1000000,5000000]
[null,"Repair or replace Gymnasium  floors.","DISTRICT WIDE",200000,200000,200000,200000,200000,1000000]
[null,"Repair or replace Stadium lights.","DISTRICT WIDE",150000,150000,150000,150000,150000,750000]
[null,"Window coverings & drapes.","DISTRICT WIDE",100000,100000,100000,100000,100000,500000]
[null,"Restroom partitions.","DISTRICT WIDE",125000,125000,125000,125000,125000,625000]
[null,"Termite Treatment.","DISTRICT WIDE",100000,100000,100000,100000,100000,500000]
[null,"Replace or repair Plumbing.","DISTRICT WIDE",1800000,1800000,1800000,1800000,1800000,9000000]
[null,"Sidewalks.","DISTRICT WIDE",25000,25000,25000,25000,25000,125000]
[null,"Sealcoating, repaving, restriping.","DISTRICT WIDE",250000,250000,250000,250000,250000,1250000]
[null,"Roof repair.","DISTRICT WIDE",675000,675000,675000,675000,675000,3375000]
[null,"Replace DX equipment.","DISTRICT WIDE",950000,950000,950000,950000,950000,4750000]
[null,"Replace chalkboards & marker boards.","DISTRICT WIDE",200000,200000,200000,200000,200000,1000000]
[null,"Repair & replace lockers.","DISTRICT WIDE",300000,300000,300000,300000,300000,1500000]
[null,"Motorized bleachers.","DISTRICT WIDE",75000,75000,75000,75000,75000,375000]
[null,"Misc. Professional Services.","DISTRICT WIDE",100000,100000,100000,100000,100000,500000]
[null,"Drainage and sitework.","DISTRICT WIDE",175000,175000,175000,175000,175000,875000]
[null,"Chiller inspections.","DISTRICT WIDE",150000,150000,150000,150000,150000,750000]
[null,"Asbestos Abatement ","DISTRICT WIDE",650000,650000,650000,650000,650000,3250000]
[null,"Environmental compliance","DISTRICT WIDE",250000,250000,250000,250000,250000,1250000]
[null,"Districtwide Relocatables.","DISTRICT WIDE",350000,350000,350000,350000,350000,1750000]
[null,"Waterproofing.","DISTRICT WIDE",100000,100000,100000,100000,100000,500000]
[null,"Maintenance reimbursement.","DISTRICT WIDE",2361000,{"$nulls":4},2361000]
[null,"Replace all AHUs.","FRANK H. PETERSON ACADEMIES OF TECHNOLOGY",1500000,{"$nulls":4},1500000]
[null,"Replace windows, phase II.","JEAN RIBAULT HIGH SCHOOL",675000,{"$nulls":4},675000]
[null,"Repair brick mortar joints and renovate restroom facilities in building 7.","LORETTO ELEMENTARY",25000,{"$nulls":4},25000]
[null,"HVAC Upgrade.","MAYPORT MIDDLE SCHOOL",883199,{"$nulls":4},883199]
[null,"Replace windows and blinds throughout the school.","MERRILL ROAD ELEMENTARY",400000,{"$nulls":4},400000]
[null,"Replacement of windows in building #1 .","PAXON MIDDLE SCHOOL",400000,{"$nulls":4},400000]
[null,"Replace domestic water lines.","REGION II OFFICE",75000,{"$nulls":4},75000]
[null,"Repipe water & sewer lines and renovate restrooms.","TECHNICAL HIGH ADMINISTRATION CENTER",300000,{"$nulls":4},300000]
[null,"Repair exterior, structure, CMU and brick walls.","DISTRICT WIDE",100000,{"$nulls":4},100000]
[null,"Pre-k restroom; covered walkway","ALMACANI ELEMENTARY",65000,{"$nulls":4},65000]
[null,"Renovate bathrooms in main building.","HOGAN-SPRING GLEN ELEMENTARY",38000,{"$nulls":4},38000]
[null,"Replace football field lighting.","JEAN RIBAULT HIGH SCHOOL",75000,{"$nulls":4},75000]
[null,"Replacement of exterior doors and venetian blinds.","PAXON MIDDLE SCHOOL",200000,{"$nulls":4},200000]
[null,"Railing for front steps.","WEST RIVERSIDE ELEMENTARY",5000,{"$nulls":4},5000]
[null,"Upgrade electrical service.","DUNCAN U. FLETCHER HIGH SCHOOL",106000,{"$nulls":4},106000]
[null,"Relocate electrical & emergency panels.","HOGAN-SPRING GLEN ELEMENTARY",32000,{"$nulls":4},32000]
[null,"Repair deteriorating wall & doors.","JEAN RIBAULT HIGH SCHOOL",90000,{"$nulls":4},90000]
[null,"Replacement of existing restroom and drainage system.","PAXON MIDDLE SCHOOL",350000,{"$nulls":4},350000]
[null,"Security System for School.","WEST RIVERSIDE ELEMENTARY",5000,{"$nulls":4},5000]
[null,"Replace windows campus wide.","ARLINGTON MIDDLE SCHOOL",100000,{"$nulls":4},100000]
[null,"Resurface basketball court.","HENDRICKS AVENUE ELEMENTARY",5000,{"$nulls":4},5000]
[null,"Replace seats in auditorium.","JEAN RIBAULT HIGH SCHOOL",100000,{"$nulls":4},100000]
[null,"Two way intercom system.","LACKAWANNA ALTERNATIVE EDUCATION CENTER",75000,{"$nulls":4},75000]
[null,"Renovate two gang bathrooms in building 1.","STANTON COLLEGE PREPARATORY",200000,{"$nulls":4},200000]
[null,"Replace floor covering in the Media Center.","ARLINGTON MIDDLE SCHOOL",50000,{"$nulls":4},50000]
[null,"Additional exterior lighting to campus.","LONG BRANCH ELEMENTARY",30000,{"$nulls":4},30000]
[null,"Replace 15 exterior classroom doors.","LOVE GROVE ELEMENTARY",50000,{"$nulls":4},50000]
[null,"Replace kitchen exhaust hood with fire suppression hood in building #3.","RUTH N. UPSON ELEMENTARY",30000,{"$nulls":4},30000]
[null,"Upgrade CCTV.","A. PHILLIP RANDOLPH ACADEMIES OF TECHNOLOGY",118000,{"$nulls":4},118000]
[null,"Window replacement.","BROOKVIEW ELEMENTARY",540000,{"$nulls":4},540000]
[null,"Replace fuse panels.","FISHWEIR ELEMENTARY",95000,{"$nulls":4},95000]
[null,"Replace hood exhaust fan on kitchen roof.","LOVE GROVE ELEMENTARY",4000,{"$nulls":4},4000]
[null,"Replace wallpaper in all hallways.","MATTHEW GILBERT MIDDLE SCHOOL",175000,{"$nulls":4},175000]
[null,"Repace flooring in first and third floors of the main building.","A. PHILLIP RANDOLPH ACADEMIES OF TECHNOLOGY",75000,{"$nulls":4},75000]
[null,"Upgrade Elec. in classrooms & add security lighting.","ENGLEWOOD ELEMENTARY",150000,{"$nulls":4},150000]
[null,"Site drainage improvements.","FISHWEIR ELEMENTARY",250000,{"$nulls":4},250000]
[null,"Replace/install acoustical tiles on the walls of the cafeteria.","LAKE LUCINA ELEMENTARY",15000,{"$nulls":4},15000]
[null,"Replace existing floor covering in administration.","NORTHWESTERN MIDDLE SCHOOL",75000,{"$nulls":4},75000]
[null,"Floor covering for 25 classrooms.","WINDY HILL ELEMENTARY",40000," ",null,null,null,40000]
[null,"Replace 400 ft. sewer line.","ENGLEWOOD HIGH SCHOOL",20000,{"$nulls":4},20000]
[null,"Install ramps in front of the school.","FISHWEIR ELEMENTARY",30000,{"$nulls":4},30000]
[null,"Renovate restrooms.","RUFUS E. PAYNE ELEMENTARY",37000,{"$nulls":4},37000]
[null,"Replace hood exhaust fan on kitchen roof.","ATLANTIC BEACH ELEMENTARY",3000,{"$nulls":4},3000]
[null,"Acoustic treatment of music room.  ","DOUGLAS ANDERSON SCHOOL OF THE ARTS",50000,{"$nulls":4},50000]
[null,"Replace handrails on 2nd floor and light fixtures in walkway.","FISHWEIR ELEMENTARY",50000,{"$nulls":4},50000]
[null,"Renovate group toilets and primary bathrooms.","S. A. HULL ELEMENTARY",150000,{"$nulls":4},150000]
[null,"Replace windows.","JOSEPH STILWELL MIDDLE SCHOOL",450000,{"$nulls":4},450000]
[null,"Replace kitchen exhaust hood.","VENETIA ELEMENTARY",30000,{"$nulls":4},30000]
[null,"Replace heating system in the main building.","GARDEN CITY ELEMENTARY",250000,{"$nulls":4},250000]
[null,"Replace lighting & provide additional. ","KINGS TRAIL ELEMENTARY",150000,{"$nulls":4},150000]
[null,"Replace windows and doors.","TERRY PARKER HIGH SCHOOL",500000,{"$nulls":4},500000]
[null,"Replacement of all outside entry doors.","GARDEN CITY ELEMENTARY",15000,{"$nulls":4},15000]
[null,"Provide two-way intercom system.","HOLIDAY HILL ELEMENTARY",75000,{"$nulls":4},75000]
[null,"Upgrade electrical in computer labs.","LAKE SHORE MIDDLE SCHOOL",40000,{"$nulls":4},40000]
[null,"Replace kitchen hood fan & upgrade outside security lights","MAYPORT MIDDLE SCHOOL",15000,{"$nulls":4},15000]
[null,"New Fire Alarm System.","STANTON COLLEGE PREPARATORY",225000,{"$nulls":4},225000]
[null,"Replace covered walkway between building 1 and 2.","BILTMORE ELEMENTARY",60000,{"$nulls":4},60000]
[null,"Replace floor covering in rooms 8, 9, 10, and 14.","NORWOOD ELEMENTARY",45000,{"$nulls":4},45000]
[null,"Drainage improvements for classrooms.","PINEDALE ELEMENTARY",100000,{"$nulls":4},100000]
[null,"Replace floor covering in 14 classrooms.","SABAL PALM ELEMENTARY",45000,{"$nulls":4},45000]
[null,"Replace concrete in central corridor.","SOUTHSIDE MIDDLE SCHOOL",100000,{"$nulls":4},100000]
[null,"Improve drainage in courtyard.","BRENTWOOD ELEMENTARY",156000,{"$nulls":4},156000]
[null,"Fence kindergarten playground.","CHETS CREEK ELEMENTARY",8000,{"$nulls":4},8000]
[null,"Replace restroom floors and renovate.","EUGENE BUTLER MIDDLE SCHOOL",155000,{"$nulls":4},155000]
[null,"Replace floor covering.","GREENFIELD ELEMENTARY",104000,{"$nulls":4},104000]
[null,"Bathroom access for ESE autistic room No. 28.","PINEDALE ELEMENTARY",5000,{"$nulls":4},5000]
[null,"Upgrade electric.","ANDREW JACKSON HIGH SCHOOL",60000,{"$nulls":4},60000]
[null,"Install a fire suppression hood above stove. ","CEDAR HILLS ELEMENTARY",30000,{"$nulls":4},30000]
[null,"Replace intercom console.","JOSEPH FINEGAN ELEMENTARY",10000,{"$nulls":4},10000]
[null,"Rekey the entire building.","SAMUEL W. WOLFSON HIGH SCHOOL",50000,{"$nulls":4},50000]
[null,"Repipe main building floor heat & pneumatic controls.","WEST JACKSONVILLE ELEMENTARY",300000,{"$nulls":4},300000]
[null,"Additional electrical outlets in classrooms.","JOSEPH STILWELL MIDDLE SCHOOL",85000,{"$nulls":4},85000]
[null,"Replace football field lighting.","ANDREW JACKSON HIGH SCHOOL",75000,{"$nulls":4},75000]
[null,"Remediate the acoustical problems in the cafeteria.","FORT CAROLIINE ELEMENTARY",105000,{"$nulls":4},105000]
[null,"Replace domestic & cold water & urinals in building 1.","JACKSONVILLE HEIGHTS ELEMENTARY",380000,{"$nulls":4},380000]
[null,"Replace hood exhaust fan on kitchen roof.","SAMUEL W. WOLFSON HIGH SCHOOL",7000,{"$nulls":4},7000]
[null,"Correct and improve drainage and install irrigation.","BEAUCLERC ELEMENTARY",175000,{"$nulls":4},175000]
[null,"Gate Keepers Contingency","GATE KEEPERS",500000,{"$nulls":4},500000]
[null,"Replace all chalk boards with marker boards.","MAMIE AGNES JONES ELEMENTARY",75000,{"$nulls":4},75000]
[null,"Replacement of the HVAC & controls.","NEPTUNE BEACH ELEMENTARY",400000,{"$nulls":4},400000]
[null,"Fencing of school.","SALLYE B. MATHIS ELEMENTARY",75000,{"$nulls":4},75000]
[null,"Replace cabinets/shelves in building #1.","THOMAS JEFFERSON ELEMENTARY",65000,{"$nulls":4},65000]
[null,"HVAC repairs in main office; ceiling fans and exhaust system in warehouse.","CONSOLIDATED SERVICE CENTER",200000,{"$nulls":4},200000]
[null,"Improve wiring and increase number of classroom outlets.","CROWN POINT ELEMENTARY",50000,{"$nulls":4},50000]
[null,"Replace floor covering.","CRYSTAL SPRINGS ELEMENTARY",150000,{"$nulls":4},150000]
[null,"Upgrade security lighting by gymnasium and building No. 6.","DUNCAN U. FLETCHER MIDDLE SCHOOL",37500,{"$nulls":4},37500]
[null,"Disaster alarm system.","RAMONA BOULEVARD ELEMENTARY",2500,{"$nulls":4},2500]
[null,"Replace kitchen range hood system.","SALLYE B. MATHIS ELEMENTARY",10000,{"$nulls":4},10000]
[null,"Replace marker boards in the classrooms.","CARTER G. WOODSON ELEMENTARY",27000,{"$nulls":4},27000]
[null,"Replace telephone system.","J.E.B. STUART MIDDLE SCHOOL",60000,{"$nulls":4},60000]
[null,"Outside lighting in back of school.","JUSTINA ROAD ELEMENTARY",20000,{"$nulls":4},20000]
[null,"Staff restroom renovation.","SUSIE TOLBERT ELEMENTARY",3500,{"$nulls":4},3500]
[null,"Provide fence with gate behind pre-K classroom.","TWIN LAKES ACADEMY-ELEMENTARY",2250,{"$nulls":4},2250]
[null,"Replace floor covering in Media.","JOSEPH STILWELL MIDDLE SCHOOL",15000,{"$nulls":4},15000]
[null,"Replace intercom system.","NATHAN B. FORREST HIGH SCHOOL",75000,{"$nulls":4},75000]
[null,"Covered walkway for bus loading zone.","SOUTHSIDE ESTATES ELEMENTARY",120000,{"$nulls":4},120000]
[null,"Roof replacment.","SUSIE TOLBERT ELEMENTARY",431000,{"$nulls":4},431000]
[null,"Connect kitchen equipment to emergency generator.","TWIN LAKES ACADEMY-MIDDLE",4000,{"$nulls":4},4000]
[null,"Provide floor covering for Music Suite.","JAMES WELDON JOHNSON MIDDLE SCHOOL",10000,{"$nulls":4},10000]
[null,"New Fire Alarm.","JEFFERSON DAVIS MIDDLE SCHOOL",160000,{"$nulls":4},160000]
[null,"Covered walkway for bus loading areas.","SAN PABLO ELEMENTARY",150000,{"$nulls":4},150000]
[null,"Replace kitchen range hood system.","SUSIE TOLBERT ELEMENTARY",10000,{"$nulls":4},10000]
[null,"Repair and replace band lockers. ","TWIN LAKES ACADEMY-MIDDLE",65000,{"$nulls":4},65000]
[null,"Replace domestic waterlines & renovate restrooms.","RICHARD L. BROWN ELEMENTARY",300000,{"$nulls":4},300000,33421949,"Approved by Board"]
[null,"Rewiring for CCTV and replace distribution equipment.","JEFFERSON DAVIS MIDDLE SCHOOL",130000,{"$nulls":4},130000]
[null,"Replace floor covering.","JOHN E. FORD ELEMENTARY",207000,{"$nulls":4},207000]
[null,"Reroof entire school","MANDARIN OAKS ELEMENTARY",450000,{"$nulls":4},450000]
[null,"Remove/Repalce floor covering for entire school.","SANDALWOOD HIGH SCHOOL",750000,{"$nulls":4},750000]
[null,"Construct sidewalk on the east side of  property.","WOODLAND ACRES ELEMENTARY",13000,{"$nulls":4},13000]
[null,"Install an outside communications system.","FRANK H. PETERSON ACADEMIES OF TECHNOLOGY",50000,{"$nulls":4},50000]
[null,"Replace floor covering in Media center, Administrative Building, and classrooms.","HYDE GROVE ELEMENTARY",150000,{"$nulls":4},150000]
[null,"Canopy for bus area.","MANDARIN MIDDLE SCHOOL",80000,{"$nulls":4},80000]
[null,"Create a doorway between rooms 9 & 10 to facilitate team teaching.","R.V. DANIELS ELEMENTARY",5000,{"$nulls":4},5000]
[null,"Additional exterior lighting to campus.","LOLA M. CULVER ELEMENTARY",45000,{"$nulls":4},45000]
[null,"Repair expansion and control joints on exterior walls","MANDARIN HIGH SCHOOL",167000,{"$nulls":4},167000]
[null,"Repalce floor coverings for classrooms and office. ","PICKETT ELEMENTARY",27000,{"$nulls":4},27000]
[null,"Replace bulletin boards in building #2.","RUTH N. UPSON ELEMENTARY",15000,{"$nulls":4},15000]
[null,"Addition and repair of concrete slab on court area of playground.","SEABREEZE ELEMENTARY",20000,{"$nulls":4},20000]
[null,"Covered walkway.","ARLINGTON ELEMENTARY",125000,{"$nulls":4},125000]
[null,"Repair cracks in walls and investigate termite infiltration.","CHIMNEY LAKES ELEMENTARY",50000,{"$nulls":4},50000]
[null,"Remove all floor coverings and replace with tile.","DARNELL-COOKMAN MIDDLE SCHOOL",40000,{"$nulls":4},40000]
[null,"Outside lighting for main entrance and parking area.","HENRY F. KITE ELEMENTARY",75000,{"$nulls":4},75000]
[null,"Replace all existing chalkboards with marker boards.","PARKWOOD HEIGHTS ELEMENTARY",23000,{"$nulls":4},23000]
[null,"Install fencing in back of school. ","JEAN RIBAULT MIDDLE SCHOOL",15000,{"$nulls":4},15000]
[null,"Provide an over flow system for retention pond.","S.P. LIVINGSTON ELEMENTARY",30000,{"$nulls":4},30000]
[null,"Electrical upgrade, intercom and security lights.","TIMUCUAN ELEMENTARY",165000,{"$nulls":4},165000]
[null,"Extra lighting for back of school.","ENTERPRISE LEARNING ACADEMY",25000,{"$nulls":4},25000]
[null,"Replace ceiling tile in building 4 hallway.","JEAN RIBAULT MIDDLE SCHOOL",20000,{"$nulls":4},20000]
[null,"Replace floor covering.","LANDMARK MIDDLE SCHOOL",300000,{"$nulls":4},300000]
[null,"Two way intercom.","NORMANDY ELEMENTARY",80000,{"$nulls":4},80000]
[null,"Replace all sliding glass doors in classrooms.","ARLINGTON HEIGHTS ELEMENTARY",80000,{"$nulls":4},80000]
[null,"Renovate restrooms.","BAYVIEW ELEMENTARY",250000,{"$nulls":4},250000]
[null,"Renovation of all toilets.","NORMANDY ELEMENTARY",300000,{"$nulls":4},300000]
[null,"Replace unit ventilators and controls in all classrooms.","SAN MATEO ELEMENTARY",150000,{"$nulls":4},150000]
[null,"Replace all windows, wall systems and transit system.","NORMANDY ELEMENTARY",380000,{"$nulls":4},380000]
[null,"Two-way intercom system.","PINE ESTATES ELEMENTARY",65000,{"$nulls":4},65000]
[null,"Upgrade Intercom System.","RUTHERFORD M. V. ALTERNATIVE EDUCATIONAL CENTER",55000,{"$nulls":4},55000]
[null,"Replace or resurface tile.","ANDREW A. ROBINSON ELEMENTARY",16000,{"$nulls":4},16000]
[null,"Replace auditorium seats/asbestos vinyl floor tiles in entire school and stage curtains.","NATHAN B. FORREST HIGH SCHOOL",350000,{"$nulls":4},350000]
[null,"Window replacement.","PAXON HIGH SCHOOL",750000,{"$nulls":4},750000]
[null,"Replace worn floor coverings.","ANDREW A. ROBINSON ELEMENTARY",150000,{"$nulls":4},150000]
[null,"Replace chiller and controls.","PAXON MIDDLE SCHOOL",250000,{"$nulls":4},250000]
[null,"Repair and refinish damaged stage floor in auditorium.","ROBERT E. LEE HIGH SCHOOL",30000,{"$nulls":4},30000]
[null,"Replace television wiring and distribution system.","BALDWIN MIDDLE/HIGH SCHOOL",70000,{"$nulls":4},70000]
[null,"Replace windows over fire doors in all classrooms in building 1.","JOHN LOVE ELEMENTARY",7000,{"$nulls":4},7000]
[null,"Install emergency elevator, exit doors, nonslip vinyl on stairwells, emergency fencing.","MT. HERMAN EXCEPTIONAL STUDENT CENTER",250000,{"$nulls":4},250000]
[null,"Replace auditorium seats.","ORTEGA ELEMENTARY",40000,{"$nulls":4},40000]
[null,"Add security lighting to school.","PALM AVENUE EXCEPTIONAL STUDENT CENTER",60000,{"$nulls":4},60000]
[null,"Renovate four double bathrooms between primary classrooms.","SAN MATEO ELEMENTARY",84000,{"$nulls":4},84000]
[null,"Repair sub flooring in room 151.","CENTRAL RIVERSIDE ELEMENTARY",25000,{"$nulls":4},25000]
[null,"Additional security lights around campus.","GEORGE W. CARVER ELEMENTARY",12000,{"$nulls":4},12000]
[null,"Renovate restrooms.","MARTIN LUTHER KING ELEMENTARY",95000,{"$nulls":4},95000]
[null,"Replace concrete in rear corridor.","GEORGE W. CARVER ELEMENTARY",25000,{"$nulls":4},25000]
[null,"Install security railing.","KIRBY-SMITH MIDDLE SCHOOL",8000,{"$nulls":4},8000]
[null,"Replace floor covering in building #1.","RUTH N. UPSON ELEMENTARY",25000,{"$nulls":4},25000]
[null,"Replace all AHUs and pneumatic controls.","A. PHILLIP RANDOLPH ACADEMIES OF TECHNOLOGY",1800000,{"$nulls":4},1800000]
[null,"Repair floor covering in auditorium.","FISHWEIR ELEMENTARY",3000,{"$nulls":4},3000]
[null,"Roofing gutters around the school.","LAKE FOREST ELEMENTARY",150000,{"$nulls":4},150000]
[null,"Replace existing plumbing in restrooms & install additional water fountain.","NORMANDY VILLAGE ELEMENTARY",275000,{"$nulls":4},275000]
[null,"Upgrade of playground equipment area.","ST. CLAIR EVANS ACADEMY",150000,{"$nulls":4},150000]
[null,"Floor covering in office area and multi purpose room, renovate existing bathrooms.","TIMUCUAN ELEMENTARY",280000,{"$nulls":4},280000]
[null,"Install controls & provide a well for cooling tower.","CRYSTAL SPRINGS ELEMENTARY",200000,{"$nulls":4},200000]
[null,"Repair/replace 600 lockers. ","JEAN RIBAULT MIDDLE SCHOOL",40000,{"$nulls":4},40000]
[null,"Repair floors in building 1.","SADIE T. TILLIS ELEMENTARY",100000,{"$nulls":4},100000]
[null,"Resurface school bus loading zone and extend parking.","BAYVIEW ELEMENTARY",50000,{"$nulls":4},50000]
[null,"Correct drainage around classrooms.","GREGORY DRIVE ELEMENTARY",65000,{"$nulls":4},65000]
[null,"Install lockers in band room.","KIRBY-SMITH MIDDLE SCHOOL",53000,{"$nulls":4},53000]
[null,"Safety lighting in the parking lots-front and rear.","DINSMORE ELEMENTARY",30000,{"$nulls":4},30000]
[null,"Replace covered walkway. ","HYDE PARK ELEMENTARY",45000,{"$nulls":4},45000]
[null,"Install concrete slab behind new building #17.","SALLYE B. MATHIS ELEMENTARY",59000,{"$nulls":4},59000]
[null,"Install a school sign. Landscaping of  grounds.","MARTIN LUTHER KING ELEMENTARY",50000,{"$nulls":4},50000]
[null,"Replace and repair existing walkways.","STONEWALL JACKSON ELEMENTARY",10000,{"$nulls":4},10000]
[null,"Upgrade to CCTV system.","FIRST COAST HIGH SCHOOL",150000,{"$nulls":4},150000]
[null,"Install a new walkway from the courtyard to the building.","STONEWALL JACKSON ELEMENTARY",15000,{"$nulls":4},15000]
[null,"Remove paint from front railing.","CENTRAL RIVERSIDE ELEMENTARY",10000,{"$nulls":4},10000]
[null,"Install CCTV.","WESCONNETT ELEMENTARY",75000,{"$nulls":4},75000]
[null,"Replace floor coverings & ceiling tiles.","WHITEHOUSE ELEMENTARY",120000,{"$nulls":4},120000]
[null,"Reroof entire school.","J.E.B. STUART MIDDLE SCHOOL",1942000,{"$nulls":4},1942000]
[null,"Resurface parking area, install drainage and provide additional parking spaces.","OAK HILL ELEMENTARY",130000,{"$nulls":4},130000]
[null,"Reroof building 9.","OAK HILL ELEMENTARY",75000,{"$nulls":4},75000]
[null,"Replace windows and transit panels.","HYDE PARK ELEMENTARY",380000,{"$nulls":4},380000]
[{"$nulls":8},0]
[null,"Maintenance, Repair, and Renovation Totals",null,46262949,15364000,15364000,15364000,15364000,107718949," "]
[null," Less projected PECO Maintenance Funds (235.435(1))",null,9212698,6754951,6237314,6044804,6061916,34311683]
["1.","DUVAL Total",null,37050251,8609049,9126686,9319196,9302084,73407266]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[{"$nulls":8},0]
[null,"New Elem School \"U\" Increase.",null,248858," ",null,null,null,248858]
[null,"Woodland Acres, School wide renovation",null,851142,{"$nulls":4},851142]
[null,"Oceanway Elementary Conversion to Middle School (1200 Capacity)",null,8837900,{"$nulls":4},8837900]
[null,"Arlington Middle ESE Improvement",null,684500,{"$nulls":4},684500]
[null,"Terry Parker SED, Plexiglas windows, drainage, covered walkways.",null,2500000,{"$nulls":4},2500000]
[null,"Montessori Improvements",null,6779099," ",null,null,null,6779099]
[null,"Andrew Jackson HS, 4 new classrooms, parking and Athletics.",null,1397500,{"$nulls":4},1397500]
[null,"Seabreeze ES, New cafeteria, media and administration areas.",null,2877600,{"$nulls":4},2877600]
[null,"Mandarin Middle ESE Improvements.",null,1100000,{"$nulls":4},1100000]
[null,"Technology for Existing Schools Distict Wide",null,10854394,{"$nulls":4},10854394]
[null,"Gender Equity/Athletics/PE District Wide",null,1500000,{"$nulls":4},1500000]
[null,"ADA Requirements District Wide",null,500000,{"$nulls":4},500000]
[null,"Portables - Phase-out and upgrade to standards.",null,1500000,{"$nulls":4},1500000]
[null,"Land Acquisition - District Wide",null,250000,{"$nulls":4},250000]
[null,"Capitalized Expenses - District Wide",null,1500000,{"$nulls":4},1500000]
[null,"Fishweir ES, New cafetria, remodel administration & restrooms.",null,null,2188900,null,null,null,2188900]
[null,"Paxon Middle, School wide renovation and remodeling.",null,null,12327133,null,null,null,12327133]
[null,"Paxon Advanced Studies, School wide renovation and remodeling.",null,null,1000000,null,null,null,1000000]
[null,"Technology for Existing Schools Distict Wide",null,null,13429639,null,null,null,13429639]
[null,"Gender Equity/Athletics/PE District Wide",null,null,1500000,null,null,null,1500000]
[null,"ADA Requirements District Wide",null,null,500000,null,null,null,500000]
[null,"Portables - Phase-out and upgrade to standards.",null,null,1500000,null,null,null,1500000]
[null,"Land Acquisition - District Wide",null,null,1000000,null,null,null,1000000]
[null,"Arlington Middle ESE Improvement - Continued from 01/02.",null,null,2500000,null,null,null,2500000]
[null,"Capitalized Expenses - District Wide",null,null,1500000,null,null,null,1500000]
[null,"Arlington ES, Enlarge media center, 2 new classrooms & Intercom.",null,null,null,2127200,null,null,2127200]
[null,"Pickett ES, New media center, renovate admin area and all restrooms.",null,null,null,2339000,null,null,2339000]
[null,"Wolfson HS, Expand media ctr, & cafeteria. Renovate parking & fencing.",null,null,null,4334486,null,null,4334486]
[null,"Ribault Middle ESE Improvements.",null,null,null,1884650,null,null,1884650]
[null,"duPont Middle Sch., 10 new classrooms to replace portables.",null,null,null,2623000,null,null,2623000]
[null,"Joseph Stilwell Middle Sch., Enlarge bus area, walkways & parking.",null,null,null,683610,null,null,683610]
[null,"Windy Hill ES,  Covered walkways, drainage & window replacement.",null,null,null,726050,null,null,726050]
[null,"ESE Requirements - District Wide",null,null,null,1500000,null,null,1500000]
[null,"Technology for Existing Schools Distict Wide",null,null,null,13485498,null,null,13485498]
[null,"Gender Equity/Athletics/PE District Wide",null,null,null,1500000,null,null,1500000]
[null,"ADA Requirements District Wide",null,null,null,2000000,null,null,2000000]
[null,"Portables - Phase-out and upgrade to standards.",null,null,null,1500000,null,null,1500000]
[null,"Land Acquisition - District Wide",null,null,null,1000000,null,null,1000000]
[null,"Capitalized Expenses - District Wide",null,null,null,1500000,null,null,1500000]
[null,"Arlington Middle School, School wide renovation & remodeling.",{"$nulls":4},3673147,null,3673147]
[null,"New Middle School \"DD\" (Westside/Argyle) (1200 Capacity)",{"$nulls":4},21064806,null,21064806]
[null,"Cedar Hills ES, School wide renovation and remodeling.",{"$nulls":4},2359400,null,2359400]
[null,"New High School \"AAA\" (1800 Capacity)",{"$nulls":4},42972000,null,42972000]
[null,"Hogan-Spring Glen ES, New cafetria & remodel old into classrooms.",{"$nulls":4},2732380,null,2732380]
[null,"Arlington Heights ES, Renovate administration, media ctr and speech room.",{"$nulls":4},2441100,null,2441100]
[null,"Nathan B. Forrest HS, Remodel media ctr, restrooms, floors & lockers.",{"$nulls":4},2734340,null,2734340]
[null,"Venetia ES, New covered walkways & upgrade fire alarm.",{"$nulls":4},403250,null,403250]
[null,"Robert E. Lee HS, Renovate bus loop, cafeteria & band room.",{"$nulls":4},2750400,null,2750400]
[null,"First Coast HS, New covered walkways & renovate mechanical.",{"$nulls":4},3137600,null,3137600]
[null,"Jefferson Davis Middle Sch.  Renovate restrooms.",{"$nulls":4},500000,null,500000]
[null,"Technology for Existing Schools Distict Wide",{"$nulls":4},7855314,null,7855314]
[null,"Gender Equity/Athletics/PE District Wide",{"$nulls":4},1500000,null,1500000]
[null,"ADA Requirements District Wide",{"$nulls":4},500000,null,500000]
[null,"Capitalized Expenses - District Wide",{"$nulls":4},1500000,null,1500000]
[null,"North Shore ES, Renovate clasrooms, restrooms & drainage.",{"$nulls":5},11445700,11445700]
[null,"Parkwood Heights ES, Covered walkways and classroom lighting.",{"$nulls":5},1181600,1181600]
[null,"J.E.B. Stuart MS, Renovate media ctr, drainage and parent pick-up.",{"$nulls":5},1326340,1326340]
[null,"Beulah Beal Parent Center, HVAC in Auditorium.",{"$nulls":5},403550,403550]
[null,"Terry Parker SED, Plexiglas windows, drainage, covered walkways.",{"$nulls":5},752890,752890]
[null,"Technology for Existing Schools Distict Wide",{"$nulls":5},11259619,11259619]
[null,"Gender Equity/Athletics/PE District Wide",{"$nulls":5},500000,500000]
[null,"ADA Requirements District Wide",{"$nulls":5},1500000,1500000]
[null,"Land Acquisition - District Wide",{"$nulls":5},3500000,3500000]
[null,"Capitalized Expenses - District Wide",{"$nulls":5},1500000,1500000]
[{"$nulls":8},0]
["2 .","DUVAL Total",null,41380993,37445672,37203494,96123737,33369699,245523595]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"2000-01 FISH Satisfactory","Actual 2000-01","Actual 2000-01","Actual 2000-01","New Stu Capacity to","Projected 2005-06","Projected 2005-06"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[{"$nulls":4}," "]
[6,"M.V. RUTHERFORD ",409,409,179,0.44,null,92,0.22]
[8,"J. ALLEN AXSON ELEMENTARY",394,394,271,0.69,null,350,0.89]
[10,"LACKAWANNA  - ALT. FACILITY",19,19,91,4.79,null,31,1.63]
[11,"BEULAH BEAL  - ALT. FACILITY",52,52,181,3.48,null,89,1.71]
[12,"WEST RIVERSIDE ELEMENTARY",455,455,374,0.82,null,380,0.84]
[13,"LOLA M. CULVER ELEMENTARY",309,309,277,0.9,null,289,0.94]
[14,"GRAND PARK ",455,409,132,0.32,null,59,0.14]
[15,"BRENTWOOD ELEMENTARY",402,402,307,0.76,null,300,0.75]
[16,"ORTEGA ELEMENTARY",305,305,372,1.22,null,350,1.15]
[18,"CENTRAL RIVERSIDE",477,477,447,0.94,null,500,1.05]
[19,"RUTH N. UPSON ELEMENTARY",545,545,492,0.9,null,426,0.78]
[20,"FISHWEIR ELEMENTARY",399,399,329,0.82,null,345,0.86]
[21,"ANNIE R. MORGAN ",519,519,526,1.01,null,501,0.97]
[23,"NORWOOD ELEMENTARY",223,223,164,0.74,null,174,0.78]
[25,"KIRBY-SMITH MIDDLE SCHOOL",978,880,983,1.12,null,938,1.07]
[30,"LORETTO ELEMENTARY",1421,1421,1268,0.89,null,1257,0.88]
[31,"LANDON MIDDLE SCHOOL",1314,1182,470,0.4,null,410,0.35]
[32,"MARINE SCIENCE CENTER",146,131,34,0.26,null,12,0.09]
[33,"ROBERT E. LEE HIGH SCHOOL",1589,1509,1202,0.8,null,1079,0.72]
[35,"ANDREW JACKSON HIGH ",1361,1224,1492,1.22,null,1470,1.2]
[37,"HENRY F. KITE ELEMENTARY",343,343,347,1.01,null,350,1.02]
[38,"BALDWIN HIGH",569,512,425,0.83,null,430,0.84]
[38,"BALDWIN MIDDLE",525,472,425,0.9,null,430,0.91]
[45,"DINSMORE ELEMENTARY",515,515,417,0.81,null,490,0.95]
[46,"ARLINGTON ELEMENTARY",386,386,342,0.89,null,334,0.87]
[48,"THOMAS JEFFERSON",499,499,562,1.13,null,597,1.2]
[51,"WHITEHOUSE ELEMENTARY",579,579,565,0.98,null,560,0.97]
[57,"WESCONNETT ELEMENTARY",384,384,338,0.88,null,341,0.89]
[59,"GARDEN CITY ELEMENTARY",534,534,546,1.02,null,608,1.14]
[61,"OCEANWAY ELEMENTARY",824,824,625,0.76,null,816,0.99]
[63,"DUNCAN U. FLETCHER MIDDLE",1448,1303,1539,1.18,null,1740,1.34]
[64,"HOGAN-SPRING GLEN ",615,615,424,0.69,null,449,0.73]
[65,"ATLANTIC BEACH ELEM",647,647,496,0.77,null,449,0.69]
[66,"ALFRED I. DUPONT MIDDLE ",1411,1269,1297,1.02,null,1161,0.91]
[68,"VENETIA ELEMENTARY",484,484,400,0.83,null,421,0.87]
[69,"LAKE SHORE MIDDLE SCHOOL",1495,1345,1086,0.81,null,984,0.73]
[70,"NORTH SHORE ELEMENTARY",710,710,487,0.69,null,436,0.61]
[71,"HENDRICKS AVENUE ELEM",571,571,642,1.12,null,601,1.05]
[72,"SPRING PARK ELEMENTARY",500,500,348,0.7,null,375,0.75]
[73,"JOHN LOVE ELEMENTARY",423,423,277,0.65,null,220,0.52]
[74,"LAKE FOREST ELEMENTARY",591,591,547,0.93,null,537,0.91]
[75,"PAXON HIGH SCHOOL",1189,1010,1288,1.28,null,1155,1.14]
[76,"SOUTHSIDE ESTATES ELEM",656,656,635,0.97,null,638,0.97]
[77,"HYDE PARK ELEMENTARY",649,649,539,0.83,null,555,0.86]
[78,"BILTMORE ELEMENTARY",520,520,377,0.73,null,355,0.68]
[79,"RAMONA BOULEVARD ELEM",611,611,426,0.7,null,446,0.73]
[80,"SAN PABLO ELEMENTARY",686,686,525,0.77,null,534,0.78]
[82,"LOVE GROVE ELEMENTARY",775,775,547,0.71,null,516,0.67]
[83,"SAN JOSE ELEMENTARY",767,767,867,1.13,null,830,1.08]
[84,"BAYVIEW ELEMENTARY",435,435,452,1.04,null,465,1.07]
[85,"LAKE LUCINA ELEMENTARY",580,580,550,0.95,null,535,0.92]
[86,"TERRY PARKER HIGH SCHOOL",1865,1771,2083,1.18,38,2004,1.11]
[87,"ENGLEWOOD ELEMENTARY",501,501,525,1.05,null,525,1.05]
[88,"JOHN STOCKTON ELEMENTARY",438,438,491,1.12,null,450,1.03]
[89,"WOODLAND ACRES ELEM",889,889,689,0.78,null,736,0.83]
[90,"ENGLEWOOD HIGH SCHOOL",1686,1601,1651,1.03,null,1751,1.09]
[91,"SALLYE B. MATHIS ELEM",537,537,385,0.72,null,354,0.66]
[92,"PAXON MIDDLE SCHOOL",1149,1034,938,0.91,null,922,0.89]
[93,"PINEDALE ELEMENTARY",862,862,707,0.82,null,670,0.78]
[94,"WINDY HILL ELEMENTARY",666,666,810,1.22,null,800,1.2]
[95,"RUTLEDGE H. PEARSON ELEM",571,571,352,0.62,null,351,0.61]
[96,"JEAN RIBAULT HIGH SCHOOL",1749,1661,1379,0.83,null,1250,0.75]
[97,"CEDAR HILLS ELEMENTARY",554,554,390,0.7,null,301,0.54]
[98,"TIMUCUAN ELEMENTARY",760,760,622,0.82,null,645,0.85]
[99,"HIGHLANDS ELEMENTARY",630,630,564,0.9,null,597,0.95]
[106,"LONG BRANCH ELEMENTARY",369,369,342,0.93,null,250,0.68]
[107,"DOUGLAS ANDERSON ",924,785,916,1.17,null,944,1.2]
[116,"SADIE TILLIS ELEMENTARY",538,538,445,0.83,null,489,0.91]
[124,"SAINT CLAIRE EVANS ACADEMY",734,734,597,0.81,null,599,0.82]
[128,"SUSIE TOLBERT ELEMENTARY",598,598,642,1.07,null,625,1.05]
[143,"WEST JACKSONVILLE ELEM",416,416,425,1.02,null,430,1.03]
[144,"JACKSONVILLE BEACH ELE",513,513,635,1.24,null,615,1.2]
[145,"DARNELL-COOKMAN MIDDLE",1052,946,1145,1.21,null,1120,1.18]
[146,"MATTHEW GILBERT MIDDLE",957,861,800,0.93,null,805,0.93]
[148,"RICHARD L. BROWN ELEM",861,861,740,0.86,null,701,0.81]
[149,"S.P. LIVINGSTON ELEMENTARY",982,982,631,0.64,null,599,0.61]
[152,"JAMES WELDON JOHNSON ",1027,924,1214,1.31,null,1155,1.25]
[153,"STANTON PREP COLLEGE",1948,1850,1471,0.8,null,1493,0.81]
[154,"JOHN E. FORD ELEMENTARY",828,828,715,0.86,null,710,0.86]
[155,"NORTHWESTERN MIDDLE ",1044,939,759,0.81,null,720,0.77]
[157,"MARY McLEOD BETHUNE ELEM",728,728,373,0.51,null,345,0.47]
[158,"GEORGE WASHINGTON CARVER",682,682,422,0.62,null,457,0.67]
[159,"PINE FOREST ELEMENTARY",453,453,385,0.85,null,365,0.81]
[162,"R. V. DANIELS ELEMENTARY",501,501,310,0.62,null,360,0.72]
[163,"RUFUS E. PAYNE ELEMENTARY",718,718,496,0.69,null,460,0.64]
[164,"Mt. HERMAN EXC CTR",266,266,151,0.57,null,115,0.43]
[165,"WILLIAM M. RAINES HIGH ",1970,1871,1729,0.92,null,1620,0.87]
[166,"CARTER G. WOODSON ELEM",684,684,416,0.61,null,444,0.65]
[168,"EUGENE BUTLER MIDDLE ",1034,930,733,0.79,null,677,0.73]
[169,"S. A. HULL ELEMENTARY",444,444,290,0.65,null,343,0.77]
[170,"PALM AVENUE EXC CTR",146,146,174,1.19,null,47,0.32]
[202,"REYNOLDS LANE ELEMENTARY",580,580,395,0.68,null,411,0.71]
[203,"KINGS TRAIL ELEMENTARY",653,653,443,0.68,null,430,0.66]
[204,"NORMANDY ELEMENTARY",339,339,175,0.52,null,175,0.52]
[205,"PICKETT ELEMENTARY",403,403,294,0.73,null,321,0.8]
[206,"BROOKVIEW ELEMENTARY",816,816,912,1.12,null,1072,1.31]
[207,"J.E.B. STUART MIDDLE SCHOOL",1104,994,1014,1.02,null,911,0.92]
[208,"PARKWOOD HEIGHTS ELEM",645,645,567,0.88,null,595,0.92]
[209,"HOLIDAY HILL ELEMENTARY",609,609,567,0.93,null,535,0.88]
[210,"OAK HILL ELEMENTARY",827,827,577,0.7,null,545,0.66]
[211,"SOUTHSIDE MIDDLE SCHOOL",1305,1174,1202,1.02,null,967,0.82]
[212,"JEAN RIBAULT MIDDLE SCHOOL",1549,1431,1031,0.72,null,927,0.65]
[213,"ARLINGTON MIDDLE SCHOOL",1125,1020,1003,0.98,null,946,0.93]
[214,"HYDE GROVE ELEMENTARY",543,543,616,1.13,null,588,1.08]
[215,"JUSTINA ROAD ELEMENTARY",510,510,391,0.77,null,417,0.82]
[216,"JEFFERSON DAVIS MIDDLE ",1706,1535,1508,0.98,null,1371,0.89]
[218,"SAN MATEO ELEMENTARY",562,562,691,1.23,null,659,1.17]
[219,"JOSEPH STILWELL MIDDLE ",1401,1260,1192,0.95,null,1029,0.82]
[220,"MARTIN LUTHER KING ELEM",806,806,644,0.8,null,570,0.71]
[221,"NORMANDY VILLAGE ELEM",769,769,645,0.84,null,681,0.89]
[222,"GREENFIELD ELEMENTARY",621,621,538,0.87,null,560,0.9]
[223,"DUNCAN U. FLETCHER HIGH ",2500,2375,2086,0.88,null,2216,0.93]
[224,"SAMUEL W. WOLFSON HIGH ",1812,1721,1941,1.13,null,1888,1.1]
[225,"SEABREEZE ELEMENTARY",605,605,577,0.95,null,565,0.93]
[226,"CRYSTAL SPRINGS ELEM",1276,1276,1103,0.86,null,1200,0.94]
[227,"MAYPORT ELEMENTARY",1092,1092,897,0.82,null,982,0.9]
[228,"MERRILL ROAD ELEMENTARY",557,557,688,1.24,null,764,1.37]
[229,"JACKSONVILLE HEIGHTS ELEM",918,918,937,1.02,null,941,1.03]
[230,"BEAUCLERC ELEMENTARY",1157,1157,1338,1.16,null,1300,1.12]
[232,"CHIMNEY LAKES ELEMENTARY",1244,1244,1141,0.92,null,1161,0.93]
[233,"LONE STAR ELEMENTARY",733,733,895,1.22,null,906,1.24]
[234,"STONEWALL JACKSON ELEM",387,387,288,0.74,null,301,0.78]
[235,"FORT CAROLINE ELEMENTARY",844,844,740,0.88,null,715,0.85]
[236,"MAMIE AGNES JONES ELEMENTARY",554,554,454,0.82,null,425,0.77]
[237,"SANDALWOOD HIGH SCHOOL",2892,2751,2763,1,null,2914,1.06]
[238,"FORT CAROLINE MIDDLE ",1306,1176,1127,0.96,null,960,0.82]
[239,"SABAL PALM ELEMENTARY",1281,1281,1500,1.17,null,1800,1.41]
[240,"ARLINGTON HEIGHTS ELEM",549,549,568,1.03,null,516,0.94]
[241,"NATHAN B. FORREST HIGH ",1835,1743,1488,0.85,null,1505,0.86]
[242,"LOUIS SHEFFIELD ELEMENTARY",590,590,640,1.08,null,757,1.28]
[243,"GREGORY DRIVE ELEMENTARY",685,685,663,0.97,null,627,0.92]
[244,"HIGHLANDS MIDDLE SCHOOL",1737,1563,1408,0.9,null,1500,0.96]
[245,"CROWN POINT ELEMENTARY",1380,1380,1207,0.87,null,1185,0.86]
[246,"NEPTUNE BEACH ELEMENTARY",1363,1363,1038,0.76,null,1020,0.75]
[247,"JOSEPH FINEGAN ELEMENTARY",815,815,590,0.72,null,557,0.68]
[248,"EDWARD WHITE HIGH SCHOOL",2117,2106,2026,0.96,null,2068,0.98]
[249,"GREENLAND PINES ELEM",821,821,721,0.88,null,760,0.93]
[250,"PINE ESTATES ELEMENTARY",390,390,339,0.87,null,301,0.77]
[251,"TWIN LAKES ACADEMY ELEM",1090,1090,999,0.92,null,1070,0.98]
[252,"ALDEN ROAD EXC CTR",141,141,191,1.35,null,60,0.43]
[253,"TWIN LAKES ACADEMY MIDDLE",1810,1629,1636,1,null,1700,1.04]
[254,"MAYPORT MIDDLE SCHOOL",1162,1045,981,0.94,null,930,0.89]
[255,"ENTERPRISE LEARNING",1090,1090,731,0.67,null,815,0.75]
[256,"LANDMARK MIDDLE SCHOOL",1983,1784,2009,1.13,null,2288,1.28]
[257,"ALIMACANI ELEMENTARY",1236,1236,1219,0.99,null,1211,0.98]
[258,"MANDARIN OAKS ELEMENTARY",1293,1293,1231,0.95,null,1191,0.92]
[259,"MANDARIN MIDDLE SCHOOL",1900,1710,1562,0.91,null,1440,0.84]
[260,"MANDARIN HIGH SCHOOL",2474,2350,2423,1.03,null,2299,0.98]
[262,"ANDREW A. ROBINSON ELEM",1275,1275,838,0.66,null,906,0.71]
[263,"ABESS PARK ELEMENTARY",1090,1090,1001,0.92,null,1030,0.94]
[264,"CHETS CREEK ELEMENTARY",1090,1090,1325,1.22,null,1745,1.6]
[265,"FIRST COAST HIGH SCHOOL",1939,1842,1510,0.82,null,1579,0.86]
[280,"FRANK H. PETERSON ",1532,1455,981,0.67,null,1061,0.73]
[285,"A. PHILIP RANDOLPH ",1506,1430,892,0.62,null,988,0.69]
[267,"LAVILLA SCHOOL OF ARTS",850,850,992,1.17,null,990,1.16,null," "]
[]
["2a.","DUVAL Total",137741,132674,120563,0.91,38,120101,0.9]
[]
["2b.","Proposed Location of Planned Facilities within this five year plan."]
[null," "]
[null,"New Elementary \"U\" (788 Capacity) Biscayne Blvd.,"]
[null,"New Middle \"DD\" (1201 Capacity) Westside on 103rd Street.  "]
[" ","New Middle \"EE\" (1201 Capacity) Conversion of existing Oceanway Elementary school.  "]
[null,"New High School \"AAA\" (1800 Capacity) North of Duval County line, East of Southside Blvd. South of the St. Johns River, West of intercoastal to accommodate growth."]
[]
[{"$nulls":6},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 2000-01","Owner","Student Stations","as classroom space","in 2005-06","units by 2005-06","Column \"C\""]
[null,null," "," "," "," "," "," "," "]
[8,"J. ALLEN AXSON ELEMENTARY",1,"DCSB",0,1,0,-1,34]
[11,"BEULAH BEAL ",2,"DCSB",52,null,2,null,26]
[13,"LOLA M. CULVER ELEMENTARY",2,"DCSB",16,2,0,-2,51]
[14,"GRAND PARK ",10,"DCSB",243,null,10,null,247]
[16,"ORTEGA ELEMENTARY",4,"DCSB",68,null,4,null,52]
[20,"FISHWEIR ELEMENTARY",2,"DCSB",39,null,2,null,28]
[21,"ANNIE R. MORGAN ",5,"DCSB",72,null,5,null,132]
[23,"NORWOOD ELEMENTARY",3,"DCSB",35,1,2,-1,106]
[30,"LORETTO ELEMENTARY",9,"DCSB",95,2,7,-2,261]
[35,"ANDREW JACKSON HIGH ",4,"DCSB",116,4,0,-4,93]
[37,"HENRY F. KITE ELEMENTARY",1,"DCSB",8,null,1,null,13]
[38,"BALDWIN HIGH",2,"DCSB",60,null,2,null,24]
[45,"DINSMORE ELEMENTARY",1,"DCSB",8,1,0,-1,50]
[46,"ARLINGTON ELEMENTARY",1,"DCSB",26,null,1,null,15]
[48,"THOMAS JEFFERSON",1,"DCSB",0,1,0,-1,55]
[51,"WHITEHOUSE ELEMENTARY",4,"DCSB",96,null,4,null,52]
[59,"GARDEN CITY ELEMENTARY",2,"DCSB",0,2,0,-2,72]
[64,"HOGAN-SPRING GLEN ",8,"DCSB",73,4,4,-4,172]
[65,"ATLANTIC BEACH ELEM",2,"DCSB",17,2,0,-2,57]
[66,"ALFRED I. DUPONT MIDDLE ",10,"DCSB",360,10,0,-10,250]
[68,"VENETIA ELEMENTARY",1,"DCSB",30,null,1,null,25]
[69,"LAKE SHORE MIDDLE SCHOOL",21,"DCSB",437,2,19,-2,339]
[71,"HENDRICKS AVENUE ELEM",2,"DCSB",0,null,2,null,30]
[76,"SOUTHSIDE ESTATES ELEM",2,"DCSB",0,null,2,null,26]
[77,"HYDE PARK ELEMENTARY",2,"DCSB",8,2,0,-2,59]
[78,"BILTMORE ELEMENTARY",7,"DCSB",88,4,3,-4,131]
[79,"RAMONA BOULEVARD ELEM",2,"DCSB",28,null,2,null,52]
[80,"SAN PABLO ELEMENTARY",1,"DCSB",28,1,0,-1,53]
[83,"SAN JOSE ELEMENTARY",19,"DCSB",214,4,15,-4,291]
[84,"BAYVIEW ELEMENTARY",3,"DCSB",19,null,3,null,95]
[85,"LAKE LUCINA ELEMENTARY",2,"DCSB",22,null,2,null,50]
[86,"TERRY PARKER HIGH SCHOOL",6,"DCSB",248,null,6,null,137]
[87,"ENGLEWOOD ELEMENTARY",1,"DCSB",0,null,1,null,13]
[88,"JOHN STOCKTON ELEMENTARY",6,"DCSB",38,null,6,null,114]
[89,"WOODLAND ACRES ELEM",12,"DCSB",137,6,6,-6,343]
[90,"ENGLEWOOD HIGH SCHOOL",3,"DCSB",80,null,3,null,45]
[92,"PAXON MIDDLE SCHOOL",1,"DCSB",28,null,1,null,15]
[94,"WINDY HILL ELEMENTARY",10,"DCSB",194,2,8,-2,189]
[98,"TIMUCUAN",6,"DCSB",40,null,6,null,132]
[99,"HIGHLANDS ELEMENTARY",3,"DCSB",21,null,3,null,65]
[107,"DOUGLAS ANDERSON ",8,"DCSB",225,null,8,null,120]
[124,"SAINT CLAIRE EVANS ACADEMY",2,"DCSB",50,null,2,null,30]
[128,"SUSIE TOLBERT ELEMENTARY",4,"DCSB",16,null,4,null,56]
[143,"WEST JACKSONVILLE ELEM",1,"DCSB",0,null,1,null,26]
[145,"DARNELL-COOKMAN MIDDLE",5,"DCSB",109,null,5,null,86]
[148,"RICHARD L. BROWN ELEM",3,"DCSB",75,null,3,null,45]
[152,"JAMES WELDON JOHNSON ",4,"DCSB",112,null,4,null,60]
[153,"STANTON ",13,"DCSB",369,null,13,null,191]
[155,"NORTHWESTERN MIDDLE ",3,"DCSB",84,null,3,null,45]
[165,"WILLIAM M. RAINES HIGH ",1,"DCSB",0,1,0,-1,49]
[166,"CARTER G. WOODSON ELEM",4,"DCSB",75,null,4,null,92]
[170,"PALM AVENUE ",3,"DCSB",18,null,3,null,45]
[203,"KINGS TRAIL ELEMENTARY",9,"DCSB",205,null,9,null,195]
[205,"PICKETT ELEMENTARY",3,"DCSB",0,null,3,null,39]
[206,"BROOKVIEW ELEMENTARY",7,"DCSB",120,null,7,null,91]
[207,"J.E.B. STUART MIDDLE SCHOOL",2,"DCSB",28,null,2,null,16]
[208,"PARKWOOD HEIGHTS ELEM",5,"DCSB",92,null,5,0,112]
[211,"SOUTHSIDE MIDDLE SCHOOL",10,"DCSB",242,2,8,-2,177]
[212,"JEAN RIBAULT MIDDLE SCHOOL",14,"DCSB",420,null,14,null,118]
[213,"ARLINGTON MIDDLE SCHOOL",5,"DCSB",49,null,5,null,84]
[214,"HYDE GROVE ELEMENTARY",12,"DCSB",0,3,9,-3,408]
[215,"JUSTINA ROAD ELEMENTARY",1,"DCSB",22,null,1,null,13]
[216,"JEFFERSON DAVIS MIDDLE ",17,"DCSB",469,null,17,null,143]
[218,"SAN MATEO ELEMENTARY",5,"DCSB",44,1,4,-1,106]
[219,"JOSEPH STILWELL MIDDLE ",11,"DCSB",273,null,11,null,153]
[220,"MARTIN LUTHER KING ELEM",2,"DCSB",22,null,2,null,52]
[221,"NORMANDY VILLAGE ELEM",2,"DCSB",30,null,2,null,30]
[222,"GREENFIELD ELEMENTARY",3,"DCSB",35,null,3,null,75]
[223,"DUNCAN U. FLETCHER HIGH ",14,"DCSB",461,null,14,null,164]
[224,"SAMUEL W. WOLFSON HIGH ",16,"DCSB",351,4,12,-4,413]
[225,"SEABREEZE ELEMENTARY",7,"DCSB",112,null,7,null,158]
[227,"MAYPORT ELEMENTARY",8,"DCSB",87,null,8,null,236]
[228,"MERRILL ROAD ELEMENTARY",6,"DCSB",110,1,5,-1,151]
[229,"JACKSONVILLE HEIGHTS ELEMENTARY",2,"DCSB",47,null,2,null,51]
[233,"LONE STAR ELEMENTARY",3,"DCSB",40,1,2,-1,80]
[235,"FORT CAROLINE ELEMENTARY",8,"DCSB",186,null,8,null,202]
[236,"MAMIE AGNES JONES ELEMENTARY",2,"DCSB",19,1,1,-1,64]
[238,"FORT CAROLINE MIDDLE ",12,"DCSB",249,null,12,null,204]
[239,"SABAL PALM ELEMENTARY",4,"DCSB",100,null,4,null,60]
[240,"ARLINGTON HEIGHTS ELEM",5,"DCSB",30,null,5,null,67]
[241,"NATHAN B. FORREST HIGH ",13,"DCSB",343,1,12,-1,197]
[242,"LOUIS SHEFFIELD ELEMENTARY",1,"DCSB",0,null,1,null,26]
[243,"GREGORY DRIVE ELEMENTARY",7,"DCSB",106,null,7,null,135]
[244,"HIGHLANDS MIDDLE SCHOOL",19,"DCSB",522,null,19,null,285]
[247,"JOSEPH FINEGAN ELEMENTARY",1,"DCSB",18,null,1,null,26]
[248,"EDWARD WHITE HIGH SCHOOL",9,"DCSB",231,null,9,null,160]
[250,"PINE ESTATES ELEMENTARY",5,"DCSB",55,null,5,null,103]
[264,"CHETS CREEK ELEMENTARY",4,"DCSB",100,null,4,null,60]
[]
["2c1.","DUVAL Total",489,null,9395,66,423,-66,"Avg Age 19.41"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06","5 YEAR TOTAL"]
[]
[8,"J. ALLEN AXSON ELEMENTARY",1,1,0,0,0,0,1]
[13,"LOLA M. CULVER ELEMENTARY",2,2,0,0,0,0,2]
[23,"NORWOOD ELEMENTARY",1,1,0,0,0,0,1]
[30,"LORETTO ELEMENTARY",2,2,0,0,0,0,2]
[35,"ANDREW JACKSON HIGH ",4,4,0,0,0,0,4]
[45,"DINSMORE ELEMENTARY",1,1,0,0,0,0,1]
[48,"THOMAS JEFFERSON",1,1,0,0,0,0,1]
[59,"GARDEN CITY ELEMENTARY",2,2,0,0,0,0,2]
[64,"HOGAN-SPRING GLEN ",4,4,0,0,0,0,4]
[65,"ATLANTIC BEACH ELEM",2,2,0,0,0,0,2]
[66,"ALFRED I. DUPONT MIDDLE ",10,10,0,0,0,0,10]
[69,"LAKE SHORE MIDDLE SCHOOL",2,2,0,0,0,0,2]
[77,"HYDE PARK ELEMENTARY",2,2,0,0,0,0,2]
[78,"BILTMORE ELEMENTARY",4,4,0,0,0,0,4]
[80,"SAN PABLO ELEMENTARY",1,1,0,0,0,0,1]
[83,"SAN JOSE ELEMENTARY",4,4,0,0,0,0,4]
[89,"WOODLAND ACRES ELEM",6,6,0,0,0,0,6]
[94,"WINDY HILL ELEMENTARY",2,2,0,0,0,0,2]
[165,"WILLIAM M. RAINES HIGH ",1,1,0,0,0,0,1]
[211,"SOUTHSIDE MIDDLE SCHOOL",2,2,0,0,0,0,2]
[214,"HYDE GROVE ELEMENTARY",3,3,0,0,0,0,3]
[218,"SAN MATEO ELEMENTARY",1,1,0,0,0,0,1]
[224,"SAMUEL W. WOLFSON HIGH ",4,4,0,0,0,0,4]
[228,"MERRILL ROAD ELEMENTARY",1,1,0,0,0,0,1]
[233,"LONE STAR ELEMENTARY",1,1,0,0,0,0,1]
[236,"MAMIE AGNES JONES ES",1,1,0,0,0,0,1]
[241,"NATHAN B. FORREST HIGH ",1,1,0,0,0,0,1]
[]
["2c2.","DUVAL Total",66,66,0,0,0,0,66]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 2000-01","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2005-06","FISH Stu. Sta.","# Years Leased "]
[null,"No Leased Facilities"]
[]
["2c3.","DUVAL Total",0,null,0,0,0,0,0]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2005-06"]
[null," "," "," "," "," "," "," "," "]
[1,"Daniel Payne Academy (6-8)",10,"Daniel Payne Academy, Inc.","1997-98",220,160,3,200]
[2,"SOS ACADEMY (6-8)",26,"Schools of Success Academy, Inc.","1997-98",650,493,3,560]
[3,"Kreative Kids Academy (K-4)",6,"Kreative Kids Youth Foundation","1999-00",150,113,3,200]
[4,"Horizons Unlimited (6-8)",10,"Horizons Unlimited, Inc.","1999-00",220,178,3,300]
[5,"Wayman Academy of the Arts (K-5)",12,"Wayman Academy, Inc.","2000-01",218,153,3,500]
[6,"Destiny Academy of Excellence (K-5)",7,"Destiny Academy, Inc.","2000-01",136,113,3,300,null,0]
[]
["2c4.","DUVAL Total",71,null,null,1594,1210,18,1210]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[]
[]
[]
[]
["2e.","Average Class Size (5 years out -- 2005-06) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","2000-01 CO-FTE","2000-01 Class size","2005-06 CO-FTE","be added (removed)","2005-06 Class size"]
[null,"All Schools Including New Ones !!!"," "," "," "," "," "," "," "]
[6,"M.V. RUTHERFORD ",20,18,179,8.95,92,null,4.6,null,"State Average","State Average","State Average","State Average","State Average","State Average"]
[8,"J. ALLEN AXSON ELEMENTARY",18,374,271,15.06,350,null,19.44,"Year",2000,2000,2000,2000,2000,2000]
[10,"LACKAWANNA  - ALT. FACILITY",23,19,91,3.96,31,null,1.35,"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[11,"BEULAH BEAL  - ALT. FACILITY",16,52,181,11.31,89,null,5.56,1,79,110,156,9213,12712,22844]
[12,"WEST RIVERSIDE ELEMENTARY",20,433,374,18.7,380,null,19,2,86,113,165,9863,13571,18853]
[13,"LOLA M. CULVER ELEMENTARY",13,276,277,21.31,289,null,22.23,3,68,128,222,14900,18106,26448]
[14,"GRAND PARK ",18,185,132,7.33,59,null,3.28]
[15,"BRENTWOOD ELEMENTARY",20,402,307,15.35,300,null,15]
[16,"ORTEGA ELEMENTARY",15,259,372,24.8,350,null,23.33]
[18,"CENTRAL RIVERSIDE",21,470,447,21.29,500,null,23.81]
[19,"RUTH N. UPSON ELEMENTARY",25,545,492,19.68,426,null,17.04]
[20,"FISHWEIR ELEMENTARY",15,294,329,21.93,345,null,23]
[21,"ANNIE R. MORGAN ",22,519,526,23.91,501,null,22.77]
[23,"NORWOOD ELEMENTARY",10,217,164,16.4,174,null,17.4]
[25,"KIRBY-SMITH MIDDLE SCHOOL",42,866,983,23.4,938,null,22.33]
[30,"LORETTO ELEMENTARY",58,1381,1268,21.86,1257,null,21.67]
[31,"LANDON MIDDLE SCHOOL",47,1021,470,10,410,null,8.72]
[32,"MARINE SCIENCE CENTER",8,146,34,4.25,12,null,1.5]
[33,"ROBERT E. LEE HIGH SCHOOL",59,1509,1202,20.37,1079,null,18.29]
[35,"ANDREW JACKSON HIGH ",54,1197,1492,27.63,1470,null,27.22]
[37,"HENRY F. KITE ELEMENTARY",13,298,347,26.69,350,null,26.92]
[38,"BALDWIN HIGH",22,565,425,19.32,430,null,19.55]
[38,"BALDWIN MIDDLE",22,529,425,19.32,430,null,19.55]
[45,"DINSMORE ELEMENTARY",20,487,417,20.85,490,null,24.5]
[46,"ARLINGTON ELEMENTARY",16,350,342,21.38,334,2,18.56]
[48,"THOMAS JEFFERSON",22,488,562,25.55,597,null,27.14]
[51,"WHITEHOUSE ELEMENTARY",24,566,565,23.54,560,null,23.33]
[57,"WESCONNETT ELEMENTARY",17,374,338,19.88,341,null,20.06]
[59,"GARDEN CITY ELEMENTARY",22,534,546,24.82,608,null,27.64]
[61,"OCEANWAY ELEMENTARY",32,748,625,19.53,816,null,"-"]
[63,"DUNCAN U. FLETCHER MIDDLE",52,1273,1539,29.6,1740,null,33.46]
[64,"HOGAN-SPRING GLEN ",25,540,424,16.96,449,null,17.96]
[65,"ATLANTIC BEACH ELEM",30,648,496,16.53,449,null,14.97]
[66,"ALFRED I. DUPONT MIDDLE ",48,1232,1297,27.02,1161,null,24.19]
[68,"VENETIA ELEMENTARY",21,461,400,19.05,421,null,20.05]
[69,"LAKE SHORE MIDDLE SCHOOL",60,1319,1086,18.1,984,null,16.4]
[70,"NORTH SHORE ELEMENTARY",31,655,487,15.71,436,null,14.06]
[71,"HENDRICKS AVENUE ELEM",24,536,642,26.75,601,null,25.04]
[72,"SPRING PARK ELEMENTARY",17,400,348,20.47,375,null,22.06]
[73,"JOHN LOVE ELEMENTARY",19,449,277,14.58,220,null,11.58]
[74,"LAKE FOREST ELEMENTARY",22,546,547,24.86,537,null,24.41]
[75,"PAXON HIGH SCHOOL",48,971,1288,26.83,1155,null,24.06]
[76,"SOUTHSIDE ESTATES ELEM",24,554,635,26.46,638,null,26.58]
[77,"HYDE PARK ELEMENTARY",25,591,539,21.56,555,null,22.2]
[78,"BILTMORE ELEMENTARY",20,443,377,18.85,355,null,17.75]
[79,"RAMONA BOULEVARD ELEM",23,588,426,18.52,446,null,19.39]
[80,"SAN PABLO ELEMENTARY",30,701,525,17.5,534,null,17.8]
[82,"LOVE GROVE ELEMENTARY",30,734,547,18.23,516,null,17.2]
[83,"SAN JOSE ELEMENTARY",27,672,867,32.11,830,null,30.74]
[84,"BAYVIEW ELEMENTARY",18,370,452,25.11,465,null,25.83]
[85,"LAKE LUCINA ELEMENTARY",21,532,550,26.19,535,null,25.48]
[86,"TERRY PARKER HIGH SCHOOL",72,1781,2083,28.93,2004,null,27.83]
[87,"ENGLEWOOD ELEMENTARY",22,496,525,23.86,525,null,23.86]
[88,"JOHN STOCKTON ELEMENTARY",18,389,491,27.28,450,null,25]
[89,"WOODLAND ACRES ELEM",39,784,689,17.67,736,null,18.87]
[90,"ENGLEWOOD HIGH SCHOOL",63,1548,1651,26.21,1751,null,27.79]
[91,"SALLYE B. MATHIS ELEM",19,457,385,20.26,354,null,18.63]
[92,"PAXON MIDDLE SCHOOL",43,912,938,21.81,922,null,21.44]
[93,"PINEDALE ELEMENTARY",29,722,707,24.38,670,null,23.1]
[94,"WINDY HILL ELEMENTARY",33,664,810,24.55,800,null,24.24]
[95,"RUTLEDGE H. PEARSON ELEM",24,559,352,14.67,351,null,14.63]
[96,"JEAN RIBAULT HIGH SCHOOL",66,1642,1379,20.89,1250,null,18.94]
[97,"CEDAR HILLS ELEMENTARY",21,451,390,18.57,301,null,14.33]
[98,"TIMUCUAN ELEMENTARY",30,715,622,20.73,645,null,21.5]
[99,"HIGHLANDS ELEMENTARY",25,590,564,22.56,597,null,23.88]
[106,"LONG BRANCH ELEMENTARY",23,369,342,14.87,250,null,10.87]
[107,"DOUGLAS ANDERSON ",33,691,916,27.76,944,null,28.61]
[116,"SADIE TILLIS ELEMENTARY",21,513,445,21.19,489,null,23.29]
[124,"SAINT CLAIRE EVANS ACADEMY",29,734,597,20.59,599,null,20.66]
[128,"SUSIE TOLBERT ELEMENTARY",26,582,642,24.69,625,null,24.04]
[143,"WEST JACKSONVILLE ELEM",16,391,425,26.56,430,null,26.88]
[144,"JACKSONVILLE BEACH ELE",21,505,635,30.24,615,null,29.29]
[145,"DARNELL-COOKMAN MIDDLE",38,940,1145,30.13,1120,null,29.47]
[146,"MATTHEW GILBERT MIDDLE",34,861,800,23.53,805,null,23.68]
[148,"RICHARD L. BROWN ELEM",34,805,740,21.76,701,null,20.62]
[149,"S.P. LIVINGSTON ELEMENTARY",35,863,631,18.03,599,null,17.11]
[152,"JAMES WELDON JOHNSON ",37,906,1214,32.81,1155,null,31.22]
[153,"STANTON ",67,1850,1471,21.96,1493,null,22.28]
[154,"JOHN E. FORD ELEMENTARY",27,735,715,26.48,710,null,26.3]
[155,"NORTHWESTERN MIDDLE ",44,895,759,17.25,720,null,16.36]
[157,"MARY McLEOD BETHUNE ELEM",26,643,373,14.35,345,null,13.27]
[158,"GEORGE WASHINGTON CARVER",29,682,422,14.55,457,null,15.76]
[159,"PINE FOREST ELEMENTARY",16,375,385,24.06,365,null,22.81]
[162,"R. V. DANIELS ELEMENTARY",25,501,310,12.4,360,null,14.4]
[163,"RUFUS E. PAYNE ELEMENTARY",30,673,496,16.53,460,null,15.33]
[164,"Mt. HERMAN ",0,0,151,0,115,null,0]
[165,"WILLIAM M. RAINES HIGH ",77,1861,1729,22.45,1620,null,21.04]
[166,"CARTER G. WOODSON ELEM",27,632,416,15.41,444,null,16.44]
[168,"EUGENE BUTLER MIDDLE ",38,833,733,19.29,677,null,17.82]
[169,"S. A. HULL ELEMENTARY",19,416,290,15.26,343,null,18.05]
[170,"PALM AVENUE ",0,0,174,0,47,null,0]
[202,"REYNOLDS LANE ELEMENTARY",22,516,395,17.95,411,null,18.68]
[203,"KINGS TRAIL ELEMENTARY",27,629,443,16.41,430,null,15.93]
[204,"NORMANDY ELEMENTARY",14,315,175,12.5,175,null,12.5]
[205,"PICKETT ELEMENTARY",16,368,294,18.38,321,null,20.06]
[206,"BROOKVIEW ELEMENTARY",32,782,912,28.5,1072,null,33.5]
[207,"J.E.B. STUART MIDDLE SCHOOL",48,985,1014,21.13,911,null,18.98]
[208,"PARKWOOD HEIGHTS ELEM",27,633,567,21,595,null,22.04]
[209,"HOLIDAY HILL ELEMENTARY",22,542,567,25.77,535,null,24.32]
[210,"OAK HILL ELEMENTARY",38,849,577,15.18,545,null,14.34]
[211,"SOUTHSIDE MIDDLE SCHOOL",47,1125,1202,25.57,967,null,20.57]
[212,"JEAN RIBAULT MIDDLE SCHOOL",66,1600,1031,15.62,927,null,14.05]
[213,"ARLINGTON MIDDLE SCHOOL",41,879,1003,24.46,946,null,23.07]
[214,"HYDE GROVE ELEMENTARY",32,543,616,19.25,588,null,18.38]
[215,"JUSTINA ROAD ELEMENTARY",22,472,391,17.77,417,null,18.95]
[216,"JEFFERSON DAVIS MIDDLE ",61,1453,1508,24.72,1371,null,22.48]
[218,"SAN MATEO ELEMENTARY",23,545,691,30.04,659,null,28.65]
[219,"JOSEPH STILWELL MIDDLE ",49,1116,1192,24.33,1029,null,21]
[220,"MARTIN LUTHER KING ELEM",32,749,644,20.13,570,null,17.81]
[221,"NORMANDY VILLAGE ELEM",33,748,645,19.55,681,null,20.64]
[222,"GREENFIELD ELEMENTARY",26,574,538,20.69,560,null,21.54]
[223,"DUNCAN U. FLETCHER HIGH ",91,2336,2086,22.92,2216,null,24.35]
[224,"SAMUEL W. WOLFSON HIGH ",73,1709,1941,26.59,1888,null,25.86]
[225,"SEABREEZE ELEMENTARY",28,605,577,20.61,565,null,20.18]
[226,"CRYSTAL SPRINGS ELEM",43,1152,1103,25.65,1200,null,27.91]
[227,"MAYPORT ELEMENTARY",48,1111,897,18.69,982,null,20.46]
[228,"MERRILL ROAD ELEMENTARY",24,513,688,28.67,764,null,31.83]
[229,"JACKSONVILLE HEIGHTS ELEM",39,895,937,24.03,941,null,24.13]
[230,"BEAUCLERC ELEMENTARY",51,1221,1338,26.24,1300,null,25.49]
[232,"CHIMNEY LAKES ELEMENTARY",47,1194,1141,24.28,1161,null,24.7]
[233,"LONE STAR ELEMENTARY",31,711,895,28.87,906,null,29.23]
[234,"STONEWALL JACKSON ELEM",18,387,288,16,301,null,16.72]
[235,"FORT CAROLINE ELEMENTARY",34,818,740,21.76,715,null,21.03]
[236,"MAMIE AGNES JONES ELEMENTARY",32,525,454,14.19,425,null,13.28]
[237,"SANDALWOOD HIGH SCHOOL",104,2654,2763,26.57,2914,null,28.02]
[238,"FORT CAROLINE MIDDLE ",52,1165,1127,21.67,960,null,18.46]
[239,"SABAL PALM ELEMENTARY",42,1146,1500,35.71,1800,null,42.86]
[240,"ARLINGTON HEIGHTS ELEM",21,505,568,27.05,516,null,24.57]
[241,"NATHAN B. FORREST HIGH ",71,1679,1488,20.96,1505,null,21.2]
[242,"LOUIS SHEFFIELD ELEMENTARY",26,590,640,24.62,757,null,29.12]
[243,"GREGORY DRIVE ELEMENTARY",27,614,663,24.56,627,null,23.22]
[244,"HIGHLANDS MIDDLE SCHOOL",66,1543,1408,21.33,1500,null,22.73]
[245,"CROWN POINT ELEMENTARY",50,1353,1207,24.14,1185,null,23.7]
[246,"NEPTUNE BEACH ELEMENTARY",49,1332,1038,21.18,1020,null,20.82]
[247,"JOSEPH FINEGAN ELEMENTARY",35,815,590,16.86,557,null,15.91]
[248,"EDWARD WHITE HIGH SCHOOL",74,1942,2026,27.38,2068,null,27.95]
[249,"GREENLAND PINES ELEM",27,743,721,26.7,760,null,28.15]
[250,"PINE ESTATES ELEMENTARY",18,382,339,18.83,301,null,16.72]
[251,"TWIN LAKES ACADEMY ELEM",32,1045,999,31.22,1070,null,33.44]
[252,"ALDEN ROAD ",0,0,191,0,60,null,0]
[253,"TWIN LAKES ACADEMY MIDDLE",61,1577,1636,26.82,1700,null,27.87]
[254,"MAYPORT MIDDLE SCHOOL",41,984,981,23.93,930,null,22.68]
[255,"ENTERPRISE LEARNING",32,1045,731,22.84,815,null,25.47]
[256,"LANDMARK MIDDLE SCHOOL",65,1688,2009,30.91,2288,null,35.2]
[257,"ALIMACANI ELEMENTARY",47,1191,1219,25.94,1211,null,25.77]
[258,"MANDARIN OAKS ELEMENTARY",46,1194,1231,26.76,1191,null,25.89]
[259,"MANDARIN MIDDLE SCHOOL",61,1663,1562,25.61,1440,null,23.61]
[260,"MANDARIN HIGH SCHOOL",85,2309,2423,28.51,2299,null,27.05]
[262,"ANDREW A. ROBINSON ELEM",44,1180,838,19.05,906,null,20.59]
[263,"ABESS PARK EL",32,1045,1001,31.28,1030,null,32.19]
[264,"CHETS CREEK ELEMENTARY",32,1045,1325,41.41,1745,null,54.53]
[265,"FIRST COAST HIGH SCHOOL",65,1708,1510,23.23,1579,null,24.29]
[280,"FRANK H. PETERSON ",42,784,981,23.36,1061,null,25.26]
[285,"A. PHILIP RANDOLPH ",40,632,892,22.3,988,null,24.7]
[267,"LAVILLA PER. ARTS",40,858,992,24.8,990,null,24.75]
[null,"New Elementary School \"V\"",28,730,"N/A","N/A",0,28,0]
[null,"New Elementary School \"W\"",28,730,"N/A","N/A",0,28,0]
[null,"New Elementary School \"X\"",28,730,"N/A","N/A",0,28,0]
[null,"New Middle School \"CC\"",37,1142,"N/A","N/A",0,37,0]
[null,"New Elementary \"U\" ",28,730,"N/A","N/A",0,28,0]
[null,"New Middle \"DD\" ",37,1142,"N/A","N/A",0,37,0]
[null,"New Middle \"EE\" ",37,1142,"N/A","N/A",0,37,0]
[null,"New High School \"AAA\" ",48,1751,"N/A","N/A",0,48,0]
[null,null," "," "," "," "," "," "," "]
["2e.","DUVAL Total",5560,132411,120563,"District Avg 22",120101,273,"District Avg 21"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,"Site                              ",null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06","5 YEAR AVERAGE"]
[null," ",null," "," "," "," "," "," "]
[8,"J. ALLEN AXSON ELEMENTARY",null,0,0,0,0,0,0]
[11,"BEULAH BEAL ",null,52,52,52,52,52,52]
[13,"LOLA M. CULVER ELEMENTARY",null,16,0,0,0,0,3.2]
[14,"GRAND PARK ",null,243,243,243,243,243,243]
[16,"ORTEGA ELEMENTARY",null,68,68,68,68,68,68]
[20,"FISHWEIR ELEMENTARY",null,39,39,39,39,39,39]
[21,"ANNIE R. MORGAN ",null,72,72,72,72,72,72]
[23,"NORWOOD ELEMENTARY",null,35,35,35,35,35,35]
[30,"LORETTO ELEMENTARY",null,95,78,78,78,78,81.4]
[35,"ANDREW JACKSON HIGH ",null,116,56,56,56,56,68]
[37,"HENRY F. KITE ELEMENTARY",null,8,8,8,8,8,8]
[38,"BALDWIN HIGH",null,60,60,60,60,60,60]
[45,"DINSMORE ELEMENTARY",null,8,0,0,0,0,1.6]
[46,"ARLINGTON ELEMENTARY",null,26,26,26,26,26,26]
[48,"THOMAS JEFFERSON",null,0,0,0,0,0,0]
[51,"WHITEHOUSE ELEMENTARY",null,96,96,96,96,96,96]
[59,"GARDEN CITY ELEMENTARY",null,0,0,0,0,0,0]
[64,"HOGAN-SPRING GLEN ",null,73,60,60,60,60,62.6]
[65,"ATLANTIC BEACH ELEM",null,17,0,0,0,0,3.4]
[66,"ALFRED I. DUPONT MIDDLE ",null,360,28,28,28,28,94.4]
[68,"VENETIA ELEMENTARY",null,30,30,30,30,30,30]
[69,"LAKE SHORE MIDDLE SCHOOL",null,437,377,377,377,377,389]
[71,"HENDRICKS AVENUE ELEM",null,0,0,0,0,0,0]
[76,"SOUTHSIDE ESTATES ELEM",null,0,0,0,0,0,0]
[77,"HYDE PARK ELEMENTARY",null,8,0,0,0,0,1.6]
[78,"BILTMORE ELEMENTARY",null,88,28,28,28,28,40]
[79,"RAMONA BOULEVARD ELEM",null,28,28,28,28,28,28]
[80,"SAN PABLO ELEMENTARY",null,28,0,0,0,0,5.6]
[83,"SAN JOSE ELEMENTARY",null,214,114,114,114,114,134]
[84,"BAYVIEW ELEMENTARY",null,19,19,19,19,19,19]
[85,"LAKE LUCINA ELEMENTARY",null,22,22,22,22,22,22]
[86,"TERRY PARKER HIGH SCHOOL",null,248,248,248,248,248,248]
[87,"ENGLEWOOD ELEMENTARY",null,0,0,0,0,0,0]
[88,"JOHN STOCKTON ELEMENTARY",null,38,38,38,38,38,38]
[89,"WOODLAND ACRES ELEM",null,137,60,60,60,60,75.4]
[90,"ENGLEWOOD HIGH SCHOOL",null,80,80,80,80,80,80]
[92,"PAXON MIDDLE SCHOOL",null,28,28,28,28,28,28]
[94,"WINDY HILL ELEMENTARY",null,194,144,144,144,144,154]
[98,"TIMUCUAN",null,40,40,40,40,40,40]
[99,"HIGHLANDS ELEMENTARY",null,21,21,21,21,21,21]
[107,"DOUGLAS ANDERSON ",null,225,225,225,225,225,225]
[124,"SAINT CLAIRE EVANS ACADEMY",null,50,50,50,50,50,50]
[128,"SUSIE TOLBERT ELEMENTARY",null,16,16,16,16,16,16]
[143,"WEST JACKSONVILLE ELEM",null,0,0,0,0,0,0]
[145,"DARNELL-COOKMAN MIDDLE",null,109,109,109,109,109,109]
[148,"RICHARD L. BROWN ELEM",null,75,75,75,75,75,75]
[152,"JAMES WELDON JOHNSON ",null,112,112,112,112,112,112]
[153,"STANTON ",null,369,369,369,369,369,369]
[155,"NORTHWESTERN MIDDLE ",null,84,84,84,84,84,84]
[165,"WILLIAM M. RAINES HIGH ",null,0,0,0,0,0,0]
[166,"CARTER G. WOODSON ELEM",null,75,75,75,75,75,75]
[170,"PALM AVENUE ",null,18,18,18,18,18,18]
[203,"KINGS TRAIL ELEMENTARY",null,205,205,205,205,205,205]
[205,"PICKETT ELEMENTARY",null,0,0,0,0,0,0]
[206,"BROOKVIEW ELEMENTARY",null,120,120,120,120,120,120]
[207,"J.E.B. STUART MIDDLE SCHOOL",null,28,28,28,28,28,28]
[208,"PARKWOOD HEIGHTS ELEM",null,92,92,92,92,92,92]
[211,"SOUTHSIDE MIDDLE SCHOOL",null,242,192,192,192,192,202]
[212,"JEAN RIBAULT MIDDLE SCHOOL",null,420,420,420,420,420,420]
[213,"ARLINGTON MIDDLE SCHOOL",null,49,49,49,49,49,49]
[214,"HYDE GROVE ELEMENTARY",null,0,0,0,0,0,0]
[215,"JUSTINA ROAD ELEMENTARY",null,22,22,22,22,22,22]
[216,"JEFFERSON DAVIS MIDDLE ",null,469,469,469,469,469,469]
[218,"SAN MATEO ELEMENTARY",null,44,29,29,29,29,32]
[219,"JOSEPH STILWELL MIDDLE ",null,273,273,273,273,273,273]
[220,"MARTIN LUTHER KING ELEM",null,22,22,22,22,22,22]
[221,"NORMANDY VILLAGE ELEM",null,30,30,30,30,30,30]
[222,"GREENFIELD ELEMENTARY",null,35,35,35,35,35,35]
[223,"DUNCAN U. FLETCHER HIGH ",null,461,461,461,461,461,461]
[224,"SAMUEL W. WOLFSON HIGH ",null,351,239,239,239,239,261.4]
[225,"SEABREEZE ELEMENTARY",null,112,112,112,112,112,112]
[227,"MAYPORT ELEMENTARY",null,87,87,87,87,87,87]
[228,"MERRILL ROAD ELEMENTARY",null,110,85,85,85,85,90]
[229,"JACKSONVILLE HEIGHTS ELEMENTARY",null,47,47,47,47,47,47]
[233,"LONE STAR ELEMENTARY",null,40,30,30,30,30,32]
[235,"FORT CAROLINE ELEMENTARY",null,186,186,186,186,186,186]
[236,"MAMIE AGNES JONES ELEMENTARY",null,19,0,0,0,0,3.8]
[238,"FORT CAROLINE MIDDLE ",null,249,249,249,249,249,249]
[239,"SABAL PALM ELEMENTARY",null,100,100,100,100,100,100]
[240,"ARLINGTON HEIGHTS ELEM",null,30,30,30,30,30,30]
[241,"NATHAN B. FORREST HIGH ",null,343,315,315,315,315,320.6]
[242,"LOUIS SHEFFIELD ELEMENTARY",null,0,0,0,0,0,0]
[243,"GREGORY DRIVE ELEMENTARY",null,106,106,106,106,106,106]
[244,"HIGHLANDS MIDDLE SCHOOL",null,522,522,522,522,522,522]
[247,"JOSEPH FINEGAN ELEMENTARY",null,18,18,18,18,18,18]
[248,"EDWARD WHITE HIGH SCHOOL",null,231,231,231,231,231,231]
[250,"PINE ESTATES ELEMENTARY",null,55,55,55,55,55,55]
[264,"CHETS CREEK ELEMENTARY",null,100,100,100,100,100,100]
[]
["2f.","DUVAL Total students in relocatables by year",null,9395,8290,8290,8290,8290,8511]
[null,"Total number of CO-FTE students projected by year",null,120694,120446,120512,120530,120568,120550]
[null,"Percent in relocatables by year",null,0.08,0.07,0.07,0.07,0.07,0.07]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"Oceanway Elementary will be converted to a Middle School on the same site"]
[null,"Mary M. Bethune Elementary School has been temporarily closed due to environmental issues and concerns."]
[]
["3 .","The projected cost for each project identified in the tentative district facilities work program."]
[]
[]
[null,"1999 State-wide totals - Gross Sq Ft per student station: Elem low 79, avg 110, high 156; Middle low 86, avg 113, high 165; High School low 68, avg 128, high 222 "]
[null,"1999 State-wide totals - Cost per student station: Elem low 9,213, avg 12,712, high 22,844; Middle low 9,863,avg 13,571, high 18,853; High School low 14,900, avg 18,106, high  26,448 "]
[]
["3a.","2001-02 Year","Type of School (new schools only)  Others=0","2001-02","2001-02 ","2001-02","2001-02","2000 State Avg","2000 State Avg","2000 State Avg","2000 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[]
[null,"New Elem School \"U\" Increase.",1,248858,"N/A","N/A","N/A",79,110,156,{"$error":"#VALUE!"},9213,12712,22844]
[null,"Woodland Acres Elementary",0,851142,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Oceanway ES-MS Conversion",2,8837900,1334,157610,118.15,86,113,165,6625.11,9863,13571,18853]
[null,"Arlington Middle ESE",0,684500,40,7000,175,0,0,0,17112.5,0,0,0]
[null,"Terry Parker Hign SED",0,2500000,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Montessori Improvements",0,6779099,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Andrew Jackson High",0,1397000,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Seabreeze Elementary",0,2877600,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Mandarin Middle ESE",0,1100000,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[]
["3a.","DUVAL Total 2001-02",null,25276099,1374,164610,"-",null,null,null,18396]
[]
["3b.","2002-2003 Year","Type of School (new schools only)  Others=0","2002-03 ","2002-03 ","2002-03 ","2002-03 ","2000 State Avg","2000 State Avg","2000 State Avg","2001 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[]
[null,"Fishweir Elementary",0,2188900,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Paxon Middle",0,12327133,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Paxon Advanced Studies",0,1000000,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Arlington Middle ESE",0,2500000,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[]
["3b","DUVAL Total 2002-03",null,18016033,0,0,"-",null,null,null,{"$error":"#DIV/0!"}]
[]
["3c.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","2000 State Avg","2000 State Avg","2000 State Avg","2002 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[]
[null,"Arlington Elementary",0,2127200,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Pickett Elementary",0,2339000,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Wolfson High",0,4334486,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Ribault Middle ESE",0,1884650,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"duPont Middle",0,2623000,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Joseph Stilwell Middle",0,683610,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Windy Hill Elementary",0,726050,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[]
["3c","DUVAL Total 2003-04",null,14717996,0,0,"-",null,null,null,{"$error":"#DIV/0!"}]
[]
["3d.","2004-2005 Year","Type of School (new schools only)  Others=0","2004-05","2004-05","2004-05","2004-05","2000 State Avg","2000 State Avg","2000 State Avg","2003 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[]
[null,"New Middle School \"DD\" ",2,21064806,1334,148000,110.94,86,113,165,15790.71,9863,13571,18853]
[null,"New High School \"AAA\"",3,42972000,1895,284424,150.09,68,128,222,22676.52,14900,18106,26448]
[null,"Arlington Middle",0,3673147,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Cedar Hills Elementary",0,2359400,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Hogan-Spring Glen Elementary",0,2732380,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Arlington Heights Elementary",0,2441100,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Nathan B. Forrest High",0,2734340,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Venetia Elementary",0,403250,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Robert E. Lee High",0,2750400,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"First Coast High",0,3137600,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Jefferson Davis Middle",0,500000,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[]
["3d.","DUVAL Total 2004-05",null,84768423,3229,432424,133.92,null,null,null,26252.22]
[]
["3e.","2005-2006 Year","Type of School (new schools only)  Others=0","2005-06","2005-06","2005-06","2005-06","2000 State Avg","2000 State Avg","2000 State Avg","2003 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[]
[null,"North Shore Elementary",0,11445700,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Parkwood Heights Elementary",0,1181600,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"J.E.B. Stuart Middle",0,1326340,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Beulah Beal Young Parent Ctr.",0,403550,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[null,"Terry Parker High SED",0,752890,"N/A","N/A","N/A",0,0,0,{"$error":"#VALUE!"},0,0,0]
[]
[]
[]
["3e","DUVAL Total 2005-06",null,15110080,0,0," ",null,null,null,{"$error":"#DIV/0!"}]
[]
["3f.","DUVAL 5-Year Total",null,157888631,4603,597034]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,60740838,62564093,64441016,66374246,68365474,322485667]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,60740838,62564093,64441016,66374246,68365474,322485667,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null," ",{"$nulls":4},0,0]
[null,"  less amount used to purchase other vehicles",null," ",{"$nulls":4},0,0]
[null,"  less amount transferred to operating budget for maintenance/repair",null," ",{"$nulls":4},0,0]
[null,"  less amount used for maintenance/repair",null,24296335.200000003,25025637.200000003,25776406.400000002,26549698.400000002,27346189.6,128994266.80000001,0.4]
[null,"  less amount used to purchase capital outlay equipment",null,0,{"$nulls":4},0,0]
[null,"  less amount used to correct environmental problems",null,0,{"$nulls":4},0,0]
[null,"  less amount transferred to operating budget for salaries",null,0,{"$nulls":4},0,0]
[null,"  less amount used to pay debt service for s.237 loans",null,0,{"$nulls":4},0,0]
[null,"  less amount to pay debt service for COP's ",null,4817883,4493103,4356081,10324361,10322646,34314074,0.11]
[null,"  less other ",null,"-",0,0,0,0,0,0,"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,31626619.799999997,33045352.799999997,34308528.599999994,29500186.599999994,30696638.4,159177326.2,0.49,0.66]
[null,"P E C O New Construction",null,4566685,3716708,2201682,1878595,1954848,14318518,null,0.06]
[null,"C O & D S   Bond Proceeds  received on 20 March 1998",null," ",{"$nulls":4},0,null,0]
[null,"C O & D S maximum potential bond proceeds",null,474129,483612,493284,503150,513213,2467388,null,0.01]
[null,"Proceeds from 1/2 cent sales surtax authorized",null,"-",{"$nulls":4},0,null,0]
[null,"Proceeds from a s.237 loan",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from local governmental infrastructure sales surtax",null,0,0,0,0,0,0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,0,null,0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",null,0,0,0,64036806,null,64036806,null,0.27]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null," ",0,0,0,0,0,null,0]
[null,"Effort Index Grants",null,0,0,0,0,0,0]
[null,"Impact fees received",null,0,0,0,0,0,0,null,0]
[null,"Private donations",null,0,0,0,0,0,0,null,0]
[null,"Grants from local governments (half cent local gasoline tax).",null,190000,200000,200000,205000,205000,1000000,null,0]
["4.","DUVAL Total",null,36857433.8,37445672.8,37203494.599999994,96123737.6,33369699.4,241000038.2,1,1]
[null,"Plus additional Revenue from Section 6.",null,4523559,{"$nulls":4},4523559]
[null,"Total Revenue",null,41380992.8,37445672.8,37203494.599999994,96123737.6,33369699.4,245523597.2]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"New Elem School \"U\" Increase.",null,248858," ",0,0,0,248858]
[null,"Woodland Acres, School wide renovation",null,851142,0,0,0,0,851142]
[null,"Oceanway ES Conversion to MS ",1334,8837900,0,0,0,0,8837900]
[null,"Arlington Middle ESE Improvement",40,684500,0,0,0,0,684500]
[null,"Terry Parker SED, Plexiglas windows, drainage, covered walkways.",null,2500000,0,0,0,0,2500000]
[null,"Montessori Improvements",null,6779099," ",0,0,0,6779099]
[null,"Andrew Jackson HS, 4 new classrooms, parking and Athletics.",null,1397500,0,0,0,0,1397500]
[null,"Seabreeze ES, New cafeteria, media and administration areas.",null,2877600,0,0,0,0,2877600]
[null,"Mandarin Middle ESE Improvements.",null,1100000,0,0,0,0,1100000]
[null,"Technology for Existing Schools Distict Wide",null,10854394,0,0,0,0,10854394]
[null,"Gender Equity/Athletics/PE District Wide",null,1500000,0,0,0,0,1500000]
[null,"ADA Requirements District Wide",null,500000,0,0,0,0,500000]
[null,"Portables - Phase-out and upgrade to standards.",null,1500000,0,0,0,0,1500000]
[null,"Land Acquisition - District Wide",null,250000,0,0,0,0,250000]
[null,"Capitalized Expenses - District Wide",null,1500000,0,0,0,0,1500000]
[null,"Fishweir ES, New cafetria, remodel administration & restrooms.",null,0,2188900,0,0,0,2188900]
[null,"Paxon Middle, School wide renovation and remodeling.",null,0,12327133,0,0,0,12327133]
[null,"Paxon Advanced Studies, School wide renovation and remodeling.",null,0,1000000,0,0,0,1000000]
[null,"Technology for Existing Schools Distict Wide",null,0,13429639,0,0,0,13429639]
[null,"Gender Equity/Athletics/PE District Wide",null,0,1500000,0,0,0,1500000]
[null,"ADA Requirements District Wide",null,0,500000,0,0,0,500000]
[null,"Portables - Phase-out and upgrade to standards.",null,0,1500000,0,0,0,1500000]
[null,"Land Acquisition - District Wide",null,0,1000000,0,0,0,1000000]
[null,"Arlington Middle ESE Improvement - Continued from 01/02.",null,0,2500000,0,0,0,2500000]
[null,"Capitalized Expenses - District Wide",null,0,1500000,0,0,0,1500000]
[null,"Arlington ES, Enlarge media center, 2 new classrooms & Intercom.",null,0,0,2127200,0,0,2127200]
[null,"Pickett ES, New media center, renovate admin area and all restrooms.",null,0,0,2339000,0,0,2339000]
[null,"Wolfson HS, Expand media ctr, & cafeteria. Renovate parking & fencing.",null,0,0,4334486,0,0,4334486]
[null,"Ribault Middle ESE Improvements.",null,0,0,1884650,0,0,1884650]
[null,"duPont Middle Sch., 10 new classrooms to replace portables.",null,0,0,2623000,0,0,2623000]
[null,"Joseph Stilwell Middle Sch., Enlarge bus area, walkways & parking.",null,0,0,683610,0,0,683610]
[null,"Windy Hill ES,  Covered walkways, drainage & window replacement.",null,0,0,726050,0,0,726050]
[null,"ESE Requirements - District Wide",null,0,0,1500000,0,0,1500000]
[null,"Technology for Existing Schools Distict Wide",null,0,0,13485498,0,0,13485498]
[null,"Gender Equity/Athletics/PE District Wide",null,0,0,1500000,0,0,1500000]
[null,"ADA Requirements District Wide",null,0,0,2000000,0,0,2000000]
[null,"Portables - Phase-out and upgrade to standards.",null,0,0,1500000,0,0,1500000]
[null,"Land Acquisition - District Wide",null,0,0,1000000,0,0,1000000]
[null,"Capitalized Expenses - District Wide",null,0,0,1500000,0,0,1500000]
[null,"Arlington Middle School, School wide renovation & remodeling.",null,0,0,0,3673147,0,3673147]
[null,"New Middle School \"DD\"",1334,0,0,0,21064806,0,21064806]
[null,"Cedar Hills ES, School wide renovation and remodeling.",null,0,0,0,2359400,0,2359400]
[null,"New High School \"AAA\" ",1895,0,0,0,42972000,0,42972000]
[null,"Hogan-Spring Glen ES, New cafetria & remodel old into classrooms.",null,0,0,0,2732380,0,2732380]
[null,"Arlington Heights ES, Renovate administration, media ctr and speech room.",null,0,0,0,2441100,0,2441100]
[null,"Nathan B. Forrest HS, Remodel media ctr, restrooms, floors & lockers.",null,0,0,0,2734340,0,2734340]
[null,"Venetia ES, New covered walkways & upgrade fire alarm.",null,0,0,0,403250,0,403250]
[null,"Robert E. Lee HS, Renovate bus loop, cafeteria & band room.",null,0,0,0,2750400,0,2750400]
[null,"First Coast HS, New covered walkways & renovate mechanical.",null,0,0,0,3137600,0,3137600]
[null,"Jefferson Davis Middle Sch.  Renovate restrooms.",null,0,0,0,500000,0,500000]
[null,"Technology for Existing Schools Distict Wide",null,0,0,0,7855314,0,7855314]
[null,"Gender Equity/Athletics/PE District Wide",null,0,0,0,1500000,0,1500000]
[null,"ADA Requirements District Wide",null,0,0,0,500000,0,500000]
[null,"Capitalized Expenses - District Wide",null,0,0,0,1500000,0,1500000]
[null,"North Shore ES, Renovate clasrooms, restrooms & drainage.",null,0,0,0,0,11445700,11445700]
[null,"Parkwood Heights ES, Covered walkways and classroom lighting.",null,0,0,0,0,1181600,1181600]
[null,"J.E.B. Stuart MS, Renovate media ctr, drainage and parent pick-up.",null,0,0,0,0,1326340,1326340]
[null,"Beulah Beal Parent Center, HVAC in Auditorium.",null,0,0,0,0,403550,403550]
[null,"Terry Parker SED, Plexiglas windows, drainage, covered walkways.",null,0,0,0,0,752890,752890]
[null,"Technology for Existing Schools Distict Wide",null,0,0,0,0,11259619,11259619]
[null,"Gender Equity/Athletics/PE District Wide",null,0,0,0,0,500000,500000]
[null,"ADA Requirements District Wide",null,0,0,0,0,1500000,1500000]
[null,"Land Acquisition - District Wide",null,0,0,0,0,3500000,3500000]
[null,"Capitalized Expenses - District Wide",null,0,0,0,0,1500000,1500000]
[null,null,null,0,0,0,0,0,0]
[{"$nulls":8},0]
["5.","DUVAL Total",4603,41380993,37445672,37203494,96123737,33369699,245523595]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Smart School Awards",null,1000000,0,0,0,0,1000000]
[null,"K-3 Class Size Reduction",null,3523559,0,0,0,0,3523559]
["6.","DUVAL Total",null,4523559,0,0,0,0,4523559]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"None"," ",0,0,0,0,0,0]
[{"$nulls":8},0]
[{"$nulls":8},0]
["7.","DUVAL Total",0,0,0,0,0,0,0]
[]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
["Respectfully submitted this ___________ day of ____________________, 2001."]
[]
[null,"SCHOOL BOARD OF ","DUVAL  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:",{"$nulls":4},"John C. Fryer, Jr."]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ",null," ",null,null,"George L. Latimer",null,null,null," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",null,null,"Ronald A. Fagan","Project Administrator","904-390-2922",null,"faganr @educationcentral.org",null," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}