{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["5YrWkPlan"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"5YrWkPlan","index":0,"n_rows":575,"n_cols":27,"rows_kept":575,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["SCHOOL DISTRICT FACILITIES WORK PROGRAM -- WORKSHEET"]
["LEVY  SCHOOL  DISTRICT"]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted ",{"$nulls":25},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format, as you received it (not a fax), prior to September 15, 1998, and all data accurate as of July 15, 1998.",{"$nulls":25},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,null,"LEVY","Date: ==>","September 7,1999",null,"For fiscal years","1998-99 Through 2003-04"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .",null,"A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,null,"of the district."]
[{"$nulls":4},"1998-99 ","1999-00 ","2000-01 ","2001-02 ","2002-03 ","2003-2004"]
[null,null,"Project","Location","Estimated Cost","Estimated Cost","Estimated Cost","Estimated Cost","Estimated Cost","Estimated Cost","5 YEAR TOTAL"]
[null,null,"Life Safety",{"$nulls":7},0]
[{"$nulls":10},0]
[null,null,"HVAC Upgrades",{"$nulls":7},0]
[null,null,"HVAC in Buildings 08 and 11","Chiefland High School",{"$nulls":5},150000,150000]
[{"$nulls":10},0]
[{"$nulls":10},0]
[null,null,"Waste Water Retention",{"$nulls":7},0]
[{"$nulls":10},0]
[null,null,"Roofing",{"$nulls":7},0]
[{"$nulls":10},0]
[null,null,"Flooring",{"$nulls":7},0]
[{"$nulls":10},0]
[null,null,"Other",{"$nulls":7},0]
[null,null,"Covered Walkways","Williston Elementary School",{"$nulls":5},90000,90000]
[null,null,"Covered Pickup Areas","Chiefland Middle School",{"$nulls":5},30000,30000]
[null,null,"Renovate Lighting in Building 01","Chiefland Middle School",{"$nulls":5},162250,162250]
[null,null,"Convert Rooms 113, 114, and"]
[null,null,"115 in Building 01 to Administration"]
[null,null,"Student Personnel, and Itinerant"]
[null,null,"Spaces","Yankeetown School",129360,{"$nulls":5},129360]
[null,null,"Convert Rooms 103 and 105 in"]
[null,null,"Building 01 to Resource and "]
[null,null,"Compensatory","Yankeetown School",63264,{"$nulls":5},63264]
[{"$nulls":4},"1998-99 ","1999-00 ","2000-01 ","2001-02 ","2002-03 ","2003-04"]
[null,null,"Project","Location","Estimated Cost","Estimated Cost","Estimated Cost","Estimated Cost","Estimated Cost","Estimated Cost","5 YEAR TOTAL"]
[null,null,"Renovate Building 01, Rooms 101"]
[null,null,"102,104, 106, 110, 111, and 116","Yankeetown School",171456,{"$nulls":5},171456]
[null,null,"Covered Walkways","Chiefland Middle School",{"$nulls":5},105000,105000]
[null,null,"Covered Walkways","Williston Middle School",{"$nulls":5},52500,52500]
[null,null,"Parking Area","Bronson High School",{"$nulls":5},55000,55000]
[null,null,"Covered Walkways","Chiefland High School",{"$nulls":5},30000,30000]
[null,null,"Covered Walkways","Cedar Key School",{"$nulls":5},30000,30000]
[null,null,"Site Drainage","Cedar Key School",{"$nulls":5},50000,50000]
[null,null,"Covered Walkways","Hilltop School",{"$nulls":5},15000,15000]
[null,null,"Covered Walkways","Yankeetown School",{"$nulls":5},30000,30000]
[null,null,"Convert Existing Media Center to"]
[null,null,"       Art and Music Suite","Joyce Bullock Elementary",{"$nulls":5},207936,207936]
[null,null,"Renovate Building 01 and 02","Joyce Bullock Elementary",{"$nulls":5},65000,65000]
[null,null,"Convert Building 01-07 and 01-33 to"]
[null,null,"        Vocational Lab","Chiefland Middle School",{"$nulls":5},47089,47089]
[null,null,"Convert Building 01-009 to Music"]
[null,null,"         Suite","Chiefland Middle School",{"$nulls":5},178850,178850]
[null,null,"Renovate Agriculture Shop","Chiefland Middle School",{"$nulls":5},80850,80850]
[null,null,"Remodel Locker and Dressing "]
[null,null,"         Areas","Williston Middle School",{"$nulls":5},81879,81879]
[null,null,"Convert Administration to ESE","Bronson Elementary",126720,{"$nulls":5},126720]
[null,null,"Convert Media Center to Two"]
[null,null,"         Primary Classrooms","Bronson Elementary",107040,{"$nulls":5},107040]
[null,null,"Convert Two Classrooms to Music"]
[null,null,"         Room","Bronson Elementary",{"$nulls":5},81600,81600]
[null,null,"Convert One Classroom to a Skills"]
[null,null,"         Lab","Bronson Elementary",{"$nulls":5},40800,40800]
[null,null,"Convert Room 7 Building 01 to"]
[null,null,"         Stage Dressing Room","Bronson High School",{"$nulls":5},41265,41265]
[null,null,"Convert Room 11 Building 01 to"]
[null,null,"          Resource Room","Bronson High School",{"$nulls":5},44289,44289]
[null,null,"Convert Three Classrooms to"]
[null,null,"           Administration","Bronson High School",{"$nulls":5},120834,120834]
[null,null,"Convert Two Classrooms to  "]
[null,null,"           Science Demonstration","Bronson High School",{"$nulls":5},80010,80010]
[null,null,"Remodel Building 04","Chiefland High School",{"$nulls":5},343350,343350]
[null,null,"Convert Building 20 to Physical"]
[null,null,"            Education","Chiefland High School",{"$nulls":5},183204,183204]
[null,null,"Renovate Building 03","Chiefland High School",{"$nulls":5},209832,209832]
[null,null,"Renovate Building 08","Chiefland High School",{"$nulls":5},769398,769398]
[null,null,"Renovate Building 11","Chiefland High School",{"$nulls":5},170478,170478]
[null,null,"Renovate Science Labs 06-001,"]
[null,null,"            10-001, and 10-021","Chiefland High School",{"$nulls":5},132006,132006]
[null,null,"Remodel Building 04","Williston High School",{"$nulls":5},758835,758835]
[null,null,"Remodel Building 11","Williston High School",{"$nulls":5},87507,87507]
[null,null,"Remodel Building 01","Williston High School",null,405519,{"$nulls":4},405519]
[null,null,"New Cafeteria","Williston High School"]
[null,null,"Convert Locker Room and Public"]
[null,null,"          Restrooms in Building 03 to"]
[null,null,"          Public Restrooms and "]
[null,null,"          Physical Education Storage","Cedar Key School",154161,{"$nulls":5},154161]
[null,null,"Renovate Food Service","Yankeetown School",128000,{"$nulls":5},128000]
[null,null,"Convert Rooms 340, 342, 344,"]
[null,null,"346, and 350 into a Guidance"]
[null,null,"Office, Guidance Secretary's"]
[null,null,"Office,  an Itinerant office,"]
[null,null,"Textbook Storage, Teacher"]
[null,null,"Planning, Clinic, Computer "]
[null,null,"Area, Career Room, Conference"]
[null,null,"Rooms, Storage Area, and"]
[null,null,"Computer Lab","Williston High School",{"$nulls":5},367416,367416]
[null,null,"Renovate Administrative Area","Yankeetown School",31040,{"$nulls":5},31040]
[]
[{"$nulls":4},"1998-99 ","1999-00 ","2000-01 ","2001-02 ","2002-03 ","2003-04"]
[null,null,"Project","Location","Estimated Cost","Estimated Cost","Estimated Cost","Estimated Cost","Estimated Cost","Estimated Cost","5 YEAR TOTAL"]
[null,null,"Renovate Building 04","Yankeetown School",209664,{"$nulls":5},209664]
[null,null,"Convert Building 02 into Four "]
[null,null,"          General Classrooms, One Art"]
[null,null,"          Lab, One Resource Room, "]
[null,null,"          space for the following:"]
[null,null,"          Assistant Principal, Secretary,"]
[null,null,"          Storage and Custodial","Williston High School",{"$nulls":5},588735,588735]
[null,null,"Convert Locker Rooms in Building"]
[null,null,"           03 to Teacher Lounge, Dining,"]
[null,null,"           and Staff Toilets","Yankeetown School",45984,{"$nulls":5},45984]
[]
[null,null,"LEVY Total",null,1166689,405519,0,0,0,4892178,7053121]
[]
["2 .",null,"A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,null,"  projected student enrollment in K-12 programs."]
[null,null,"Project"]
[{"$nulls":4},"1998-99","1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR TOTAL"]
[null,null,"Expand Food Service, Add Teacher Lounge and Dining - Bronson Elementary",null,null,539712,{"$nulls":4},539712]
[null,null,"Multi-Purpose Room and Stage - Bronson Elementary",null,null,530592,{"$nulls":4},530592]
[null,null,"Additional Restrooms Chiefland Elementary School",null,15360,{"$nulls":5},15360]
[null,null,"Physical Education Storage Chiefland Elementary School",null,30240,{"$nulls":5},30240]
[null,null,"Multi-Purpose Room and Chair Storage Joyce Bullock Elementary School",{"$nulls":6},326880,326880]
[null,null,"Stage Storage, Dressing, and Control Booth Joyce Bullock Elementary",{"$nulls":6},203712,203712]
[null,null,"Custodial Storage Joyce Bullock Elementary",{"$nulls":6},81600,81600]
[null,null,"Media Center Joyce Bullock Elementary",{"$nulls":6},616032,616032]
[null,null,"ESE Classroom Suite Williston Elementary",{"$nulls":6},124320,124320]
[null,null,"Develop Playground Bronson Elementary",{"$nulls":6},65000,65000]
[null,null,"Construct Gymnasium Chiefland Middle",{"$nulls":6},1701315,1701315]
[null,null,"Expand Food Service Williston Middle",{"$nulls":6},359271,359271]
[null,null,"Multi-Purpose Room and Chair Storage Williston Middle",{"$nulls":6},271458,271458]
[null,null,"Administrative Suite and Media Center - Bronson Elementary",null,1456822,{"$nulls":5},1456822]
[null,null,"Six Intermediate and Two Primary Classrooms - Bronson Elementary",null,1047176,{"$nulls":5},1047176]
[null,null,"Food Service Joyce Bullock Elementary",null,1231120,{"$nulls":5},1231120]
[null,null,"Eight Primary Classrooms Joyce Bullock Elementary",null,992497,{"$nulls":5},992497]
[null,null,"One Science Demonstration and Seven Classrooms - Williston Middle",null,905123,{"$nulls":5},905123]
[null,null,"Stage and Adjoining Room Williston Middle School",{"$nulls":6},190278,190278]
[null,null,"Band Classroom and Teacher Planning Williston Middle School",{"$nulls":6},364815,364815]
[null,null,"Two Supplementary Instructional Classrooms Williston Middle School",{"$nulls":6},78210,78210]
[null,null,"Four ESE Classroom Suites Williston Middle School",{"$nulls":6},512820,512820]
[null,null,"ESE Special Vocational Lab Williston Middle School",{"$nulls":6},132165,132165]
[null,null,"ESE Resource Room Williston Middle School",{"$nulls":6},85833,85833]
[null,null,"Art Lab Williston Middle School",{"$nulls":6},152559,152559]
[null,null,"Skills Development Lab and Teacher Planning Williston Middle School",{"$nulls":6},108009,108009]
[null,null,"Expand Gym Locker and Dressing Rooms Williston Middle School",{"$nulls":6},115632,115632]
[null,null,"Art Lab Bronson High School",{"$nulls":6},195707,195707]
[null,null,"Band Suite Bronson High School",{"$nulls":6},449580,449580]
[null,null,"Expand Agriculture Lab Bronson High School",{"$nulls":6},317500,317500]
[null,null,"Four Middle School Classrooms Bronson High",null,437745,{"$nulls":5},437745]
[null,null,"Four Intermediate and Two Middle School Classrooms - Cedar Key",null,751719,{"$nulls":5},751719]
[null,null,"Supplementary Instructional Space Cedar Key School",{"$nulls":6},30195,30195]
[null,null,"ESE Classroom Cedar Key",{"$nulls":6},128205,128205]
[null,null,"New Cafeteria - Williston High",null,null,1370356,{"$nulls":4},1370356]
[null,null,"Two Resource Rooms - Cedar Key",{"$nulls":6},112860,112860]
[null,null,"Expand Food Service Yankeetown School",null,168000,{"$nulls":5},168000]
[null,null,"Construct Middle School Physical Education Facility Yankeetown School",null,1186080,{"$nulls":5},1186080]
[null,null,"Four Intermediate, Two Middle School, and Two Primary Classrooms"]
[null,null,"Yankeetown School",null,999843,{"$nulls":5},999843]
[null,null,"Two ESE, Two Primary Classrooms, One ESE Resource Room, One "]
[null,null,"Elementary Skills Lab and One Clinic - Yankeetown School",null,894432,{"$nulls":5},894432]
[null,null,"Science Demonstration Lab Yankeetown School",{"$nulls":6},146784,146784]
[null,null,"Warehouse District Office",{"$nulls":6},750000,750000]
[null,null,"Maintenance Offices, Conference, and Storage Shop Areas District Office",{"$nulls":6},450000,450000]
[null,null,"Transportation Work Bays District Office",{"$nulls":6},60000,60000]
[null,null,"Bus Wash Area District Office",{"$nulls":6},60000,60000]
[null,null,"Administrative Offices District Office",{"$nulls":6},300000,300000]
["2 .",null,"LEVY Total",null,10116157,2440660,0,0,0,8490740,21047557]
[]
[]
[null,null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.",null,"Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,null,"1997-98 FISH Satisfactory","Actual 1997-98","Actual 1997-98","Actual 1997-98","New Stu Capacity to","Projected 2003-04",null,"Projected 2003-04"]
[null,null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ",null,"Utilization"]
[null,null,"Bronson Elementary",814,814,654,0.8,0,758,null,0.92]
[null,null,"Bronson Middle/High",683,614,570,0.93,0,591,null,0.95]
[null,null,"Cedar Key",425,382,277,0.73,0,318,null,0.81]
[null,null,"Chiefland Elementary",1162,1162,832,0.72,0,948,null,0.81]
[null,null,"Chiefland Middle",625,562,425,0.76,0,482,null,0.84]
[null,null,"Chiefland High ",720,576,466,0.81,0,458,null,0.78]
[null,null,"Hilltop",76,61,45,0.74,0,65,null,1.07]
[null,null,"Joyce Bullock Elementary",630,630,519,0.82,0,592,null,0.93]
[null,null,"Williston Elementary",622,622,561,0.9,0,610,null,0.97]
[null,null,"Williston Middle",655,589,572,0.97,0,628,null,1.05]
[null,null,"Williston High School",782,625,643,1.03,null,693,null,1.1]
[null,null,"Yankeetown School",478,430,367,0.85,0,438,null,1]
["2a.",null,"LEVY Total",7672,7067,5931,0.84,0,6581,null,0.94]
[]
["2b.",null,"Proposed Location of Planned Facilities"]
[null,null,"None"]
[{"$nulls":7},"# of Units","Projected "]
["2c1.",null,"Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /",null,"Total age of all"]
[{"$nulls":6},"standards to be used","to be in use","decrease in # of",null,"relocatables in"]
[null,null,"Location","Actual # of Units in 1997-98","Owner","Student Stations","as classroom space","in 2003-04","units by 2003-04",null,"Column \"C\""]
[null,null,"Bronson Elementary",5,"LCSB",85,null,0,4,null,67]
[null,null,null,9,"FED",192,null,8,2,null,105]
[null,null,"Bronson Middle/High",2,"LCSB",54,null,0,2,null,38]
[null,null,null,2,"FED",54,null,0,2,null,18]
[null,null,"Cedar Key",7,"LCSB",178,null,4,3,null,90]
[null,null,null,2,"FED",43,null,2,0,null,20]
[null,null,"Chiefland Middle",3,"LCSB",74,null,3,0,null,39]
[null,null,null,1,"FED",10,null,1,0,null,3]
[null,null,"Hilltop ",3,"LCSB",74,null,3,0,null,18]
[null,null,"Joyce Bullock ",7,"LCSB",169,null,1,6,null,97]
[null,null,null,3,"FED",70,null,3,0,null,54]
[null,null,"Williston Elementary",1,"LCSB",25,null,1,0,null,0]
[]
[]
[]
[]
[]
[]
[null,null,"Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /",null,"Total age of all"]
[{"$nulls":6},"standards to be used","to be in use","decrease in # of",null,"relocatables in"]
[null,null,"Location","Actual # of Units in 1997-98","Owner","Student Stations","as classroom space","in 2003-04","units by 2003-04",null,"Column \"C\""]
[null,null,"Williston Middle",11,"LCSB",215,null,6,6,null,205]
[null,null,null,1,"FED",28,null,1,0,null,11]
[null,null,"Yankeetown School",9,"LCSB",212,null,3,6,null,161]
[null,null,null,3,"FED",78,null,3,0,null,32]
["2c1.",null,"LEVY Total",69,null,1561,null,39,31,null,"Avg Age 5.51"]
[]
["2c2.",null,"Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,null,"Location","Total # Units to be replaced","1998-99","1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR TOTAL"]
[null,null,"Bronson Elementary",6,null,6,{"$nulls":4},6]
[null,null,"Bronson Middle/High",4,null,4,{"$nulls":4},4]
[null,null,"Cedar Key",3,null,3,{"$nulls":4},3]
[null,null,"Chiefland Elementary",0,{"$nulls":6},0]
[null,null,"Chiefland Middle",0,{"$nulls":6},0]
[null,null,"Chiefland High",0,{"$nulls":6},0]
[null,null,"Hilltop",0,{"$nulls":6},0]
[null,null,"Joyce Bullock",6,null,6,{"$nulls":4},6]
[null,null,"Williston Elementary",0,{"$nulls":6},0]
[null,null,"Williston Middle",6,null,6,{"$nulls":4},6]
[null,null,"Williston High",0,{"$nulls":6},0]
[null,null,"Yankeetown School",6,null,6,{"$nulls":4},6]
["2c2.",null,"LEVY Total",31,0,31,0,0,0,0,31]
[]
["2c3.",null,"Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,null,"Location","# of leased classrooms 1997-98","Owner","FISH Stu. Sta.","# Years Leased ","# Leased 2003-04","FISH Stu. Sta.",null,"# Years Leased "]
[null,null,"None"]
[]
["2c3.",null,"LEVY Total",0,null,0,0,0,0,null,0]
[]
["2c4.",null,"Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":7},"Total charter students "]
[null,null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract",null,"projected for 2003-04"]
[null,null,"Chiefland - Elementary/Middle",6,"Wispering Winds ",1999,120,60,5,null,150]
[{"$nulls":4},"Charter School"]
[{"$nulls":4},"Project, Inc.",{"$nulls":5},0]
["2c4.",null,"LEVY Total",6,null,null,120,60,5,null,150]
[]
["2d.",null,"Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
{"$rows_empty":26}
["2e.",null,"Average Class Size (5 years out -- 2002-03) that will result if the district facilities work plan is fully implemented."]
[null,null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to",null,"Projected Average"]
[null,null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","1997-98 CO-FTE","1997-98 Class size","2003-04","be added (removed)",null,"2003-04 Class size"]
[]
[null,null,"Bronson Elementary",26,814,654,25,745,0,null,29]
[null,null,"Bronson Middle/High",25,614,570,23,583,0,null,23]
[null,null,"Cedar Key",20,382,277,14,310,0,null,16]
[null,null,"Chiefland Elementary",43,1162,832,19,940,0,null,22]
[null,null,"Chiefland Middle",22,562,425,19,474,0,null,21.55]
[null,null,"Chiefland High",26,576,466,18,450,0,null,17]
[null,null,"Hilltop School",3,61,45,15,65,0,null,22]
[null,null,"Joyce Bullock Elementary",26,630,519,20,584,0,null,22]
[null,null,"Williston Elementary",23,622,561,24,602,0,null,26]
[null,null,"Williston Middle",23,589,572,25,620,0,null,27]
[null,null,"Williston High",29,625,643,22,685,0,null,24]
[null,null,"Yankeetown School",21,430,367,17,430,0,null,20]
["2e.",null,"LEVY Total",287,7067,5931,20.083333333333332,6488,0,null,22.462500000000002]
[]
["2f.",null,"The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,null,"Site                              ",null,"1998-99","1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR AVERAGE"]
[null,null,"Bronson Elementary",null,222,86,86,86,86,86,113.2]
[null,null,"Bronson Middle/High",null,90,0,0,0,0,0,18]
[null,null,"Cedar Key School",null,144,44,44,44,44,44,64]
[null,null,"Chiefland Elementary",null,235,235,235,235,235,235,235]
[null,null,"Chiefland Middle",null,57,57,57,57,57,57,57]
[null,null,"Chiefland High",null,0,0,0,0,0,0,0]
[null,null,"Hilltop School",null,45,45,45,45,45,45,45]
[null,null,"Joyce Bullock Elementary",null,196,68,68,68,68,68,128]
[null,null,"Williston Elementary",null,23,23,23,23,23,23,23]
[null,null,"Williston Middle",null,211,146,146,146,146,146,183]
[null,null,"Williston High",null,0,0,0,0,0,0,0]
[null,null,"Yankeetown School",null,223,119,119,119,119,119,167]
["2f.",null,"LEVY Total students in relocatables by year",null,1863,1217,1217,1217,1217,1217,1346.2]
[null,null,"Total number of CO-FTE students projected by year",null,6023,6128,6221,6339,6398,6581,6221.8]
[null,null,"Percent in relocatables by year",null,0.31,0.2,0.2,0.19,0.19,0.18,0.22]
[]
["2g.",null,"Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[]
[null,null,"None",{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["3 .",null,"The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":9},"Year",1997,1997,1997,1997,1997,1997]
[{"$nulls":12},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":12},1,96,112,147,8492,13172,19094]
[null,null,"1997 State-wide totals - Gross Sq Ft per student station: Elem low 96, avg 112, high 147; Middle low 68, avg 108, high 131; High School low 127, avg 150, high 178 ",{"$nulls":9},2,68,108,131,11596,14169,17037]
[null,null,"1997 State-wide totals - Cost per student station: Elem low 8,341, avg 11,305, high 16,402; Middle low 7,478,avg 12,759, high 15,800; High School low 13,985, avg 20,182, high  28,785 ",{"$nulls":9},3,127,150,178,11385,25596,64760]
[]
["3a.",null,"1998-99 Year","Type of School (new schools only)  Others=0","1998-99","1998-99","1998-99","1998-99","1997 State Avg",null,"1997 State Avg","1997 State Avg","1998 Projected","1997 State Avg","1997 State Avg","1997 State Avg"]
[null,null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta",null,"GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,null,"None",{"$nulls":4},{"$error":"#DIV/0!"},0,null,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":7},{"$error":"#DIV/0!"},0,null,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":7},{"$error":"#DIV/0!"},0,null,0,0,{"$error":"#DIV/0!"},0,0,0]
["3a.",null,"LEVY Total 1998-99",null,0,0,0,{"$error":"#DIV/0!"},{"$nulls":4},{"$error":"#DIV/0!"}]
[]
[]
["3b.",null,"1999-2000 Year","Type of School (new schools only)  Others=0","1999-00","1999-00","1999-00","1999-00","1997 State Avg",null,"1997 State Avg","1997 State Avg","1999 Projected","1997 State Avg","1997 State Avg","1997 State Avg"]
[null,null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta",null,"GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,null,"None",{"$nulls":4},{"$error":"#DIV/0!"},0,null,0,0,{"$error":"#DIV/0!"},0,0,0]
["3b",null,"LEVY Total 1999-00",null,0,0,0,{"$error":"#DIV/0!"},{"$nulls":4},{"$error":"#DIV/0!"}]
[]
["3c.",null,"2000-2001 Year","Type of School (new schools only)  Others=0","2000-01","2000-01","2000-01","2000-01","1997 State Avg",null,"1997 State Avg","1997 State Avg","2000 Projected","1997 State Avg","1997 State Avg","1997 State Avg"]
[null,null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta",null,"GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,null,"None",{"$nulls":4},{"$error":"#DIV/0!"},0,null,0,0,{"$error":"#DIV/0!"},0,0,0]
["3c",null,"LEVY Total 2000-01",null,0,0,0,{"$error":"#DIV/0!"},{"$nulls":4},{"$error":"#DIV/0!"}]
[]
["3d.",null,"2001-2002 Year","Type of School (new schools only)  Others=0","2001-02","2001-02","2001-02","2001-02","1997 State Avg",null,"1997 State Avg","1997 State Avg","2001 Projected","1997 State Avg","1997 State Avg","1997 State Avg"]
[null,null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta",null,"GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,null,"None",{"$nulls":4},{"$error":"#DIV/0!"},0,null,0,0,{"$error":"#DIV/0!"},0,0,0]
["3d.",null,"LEVY Total 2001-02",null,0,0,0,{"$error":"#DIV/0!"},{"$nulls":4},{"$error":"#DIV/0!"}]
[]
["3e.",null,"2002-2003 Year","Type of School (new schools only)  Others=0","2002-03","2002-03","2002-03","2002-03","1997 State Avg",null,"1997 State Avg","1997 State Avg","2002 Projected","1997 State Avg","1997 State Avg","1997 State Avg"]
[null,null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta",null,"GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,null,"None",{"$nulls":4},{"$error":"#DIV/0!"},0,null,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":7},{"$error":"#DIV/0!"},0,null,0,0,{"$error":"#DIV/0!"},0,0,0]
["3e",null,"LEVY Total 2002-03",null,0,0,0,{"$error":"#DIV/0!"},{"$nulls":4},{"$error":"#DIV/0!"}]
[]
["3f.",null,"2003-2004 Year","Type of School (new schools only","2003-04","2003-04","2003-04","2003-04"]
[null,null,"Project Description",null,"PLANNED COST","Student Stations","Gross Sq. Ft.","GSF/per Stu Sta"]
[null,null,"None"]
[]
["3f.",null,"LEVY Total 2003-04"]
[]
[]
[]
["3f.",null,"LEVY 5-Year Total",null,0,0,0]
[]
["4 .",null,"Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[{"$nulls":4},"1998-99","1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR TOTAL"]
[null,null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,2,10]
[null,null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,1551776,1655553,1705219,1756376,1809067,1863339,10341330]
[null,null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,1551776,1655553,1705219,1756376,1809067,1863339,10341330,"2 mill Expenditures"]
[null,null,"  less amount used to purchase school busses",null,450000,472000,505620,535957,568114,602200,3133891,0.303045256267811]
[null,null,"  less amount used to purchase other vehicles",null,0,0,0,0,0,null,0,0]
[null,null,"  less amount transferred to operating budget for maintenance/repair",null,0,0,0,null,0,null,0,0]
[null,null,"  less amount used for maintenance/repair",null,0,0,0,0,0,null,0,0]
[null,null,"  less amount used to purchase capital outlay equipment",null,211650,320000,211650,211650,211650,211650,1378250,0.133275893913065]
[null,null,"  less amount used to correct environmental problems",null,0,0,0,0,0,null,0,0]
[null,null,"  less amount transferred to operating budget for salaries",null,0,0,0,0,0,null,0,0]
[null,null,"  less amount used to pay debt service for s.237 loans",null,0,0,701160,838437,null,null,1539597,0.14887804566724]
[null,null,"  less amount to pay debt service for COP's ",null,298920.59,397624,509677,508565,506717,508982,2730486,0.264036250656347]
[null,null,"  less other (please be specific)",null,0,0,0,0,0,null,0,0,"Source %"]
[null,null,"Net available 2-mills to construct new stu stations & core facilities",null,591205.4099999999,465929,-222888,-338233,522586,540507,1559106,0.150764553495537,0.08]
[null,null,"P E C O New Construction",null,339804,555250,222888,338233,419580,375306,2251061,null,0.12]
[null,null,"PECO Maintenance",null,154161,283157,408721,389164,387746,389447,2012396]
[null,null,"CO & DS maximum potential bond proceeds; pass through allocation",null,63140,{"$nulls":5},63140]
[null,null,"C O & D S   Bond Proceeds  received on 20 March 1998",null,2112026,0,0,0,0,null,2112026,null,0.11]
[null,null,"CO & DS Bond Proceeds receipt April 1999",null,null,325000,{"$nulls":4},325000]
[null,null,"C O & D S maximum potential bond proceeds","roceeds",0,0,0,0,0,null,0,null,0]
[null,null,"Proceeds from 1/2 cent sales surtax authorized",null,0,0,0,0,0,null,0,null,0]
[null,null,"Proceeds from a s.237 loan",null,0,1500000,0,0,0,null,1500000,null,0.08]
[null,null,"Proceeds from local governmental infrastructure sales surtax",null,0,0,0,0,0,null,0,null,0]
[null,null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,0,0,null,0,null,0]
[null,null,"Proceeds from Certificates of Participation (COP's)",null,0,0,0,0,0,null,0,null,0]
[null,null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,4696731,0,0,0,0,null,4696731,null,0.25]
[null,null,"Smart Schools - Yankeetown",null,4198995,{"$nulls":5},4198995]
[null,null,"Impact fees received",null,0,0,0,0,0,null,0,null,0]
[null,null,"Private donations",null,0,0,0,0,0,null,0,null,0]
[null,null,"Grants from local governments or not-for-profit organizations",null,0,0,0,0,0,null,0]
["4.",null,"LEVY Total",null,12156062.41,3129336,408721,389164,1329912,1305260,18718455]
[]
["5 .",null,"Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,null,"in paragraph 4 above."]
[]
[null,null,"Project Description",null,"1998-99","1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR TOTAL"]
[null,null,"Covered Walkways - Williston Elementary",{"$nulls":6},90000,0]
[null,null,"Covered Pickup Area - Chiefland Middle School",{"$nulls":6},30000,0]
[null,null,"Covered Walkways - Chiefland Middle School",{"$nulls":6},105000,0]
[null,null,"Covered Walkways - Williston Middle School",{"$nulls":6},52500,0]
[null,null,"Covered Walkways - Chiefland High School",{"$nulls":6},30000,0]
[null,null,"Covered Walkways - Cedar Key School",{"$nulls":6},30000,30000]
[null,null,"Convert Administration to ESE - Bronson Elementary",null,126720,{"$nulls":5},126720]
[null,null,"Convert Media to Two Primary Classrooms - Bronson Elementary",null,107040,{"$nulls":5},107040]
[null,null,"Remodel Building 01 - Williston High School",null,null,405519,{"$nulls":4},405519]
[null,null,"New Cafeteria - Williston High School",null,null,1370356,{"$nulls":4},1370356]
[null,null,"Convert Locker Room and Public Restrooms in Building 03 to Public"]
[null,null,"Restrooms and Physical Education Storage - Cedar Key School",null,154161,{"$nulls":5},154161]
[null,null,"Convert Locker Rooms in Building 03 to Teacher Lounge, Dining, and Staff"]
[null,null,"Toilets - Yankeetown School",null,45984,{"$nulls":5},45984]
[null,null,"Convert Rooms 113, 114, and 115 in Building 01 to Administration, Student"]
[null,null,"Personnel, and Itinerant Spaces - Yankeetown School",null,129360,{"$nulls":5},129360]
[null,null,"Convert Rooms 103 and 105 in Building 01 to Resource and Compensatory"]
[null,null,"Yankeetown School",null,63264,{"$nulls":5},63264]
[null,null,"Renovate Food Service - Yankeetown School",null,128000,{"$nulls":5},128000]
[null,null,"Renovate Administration Area - Yankeetown School",null,31040,{"$nulls":5},31040]
[null,null,"Renovate Building 01, Rooms 101, 102, 104, 106, 110, 111, and 116"]
[null,null,"Yankeetown School",null,171456,{"$nulls":5},171456]
[null,null,"Expand Food Service, Add Teacher Lounge and Dining - Bronson Elementary",null,null,539712,{"$nulls":4},539712]
[null,null,"Multi-Purpose Room and Stage - Bronson Elementary",null,null,530592,{"$nulls":4},530592]
[null,null,"Administrative Suite and Media Center - Bronson Elementary",null,1456822,{"$nulls":5},1456822]
[null,null,"Six Intermediate and Two Primary Classroom - Bronson Elementary",null,1047176,{"$nulls":5},1047176]
[null,null,"Additional Restroom - Chiefland Elementary",null,15360,{"$nulls":5},15360]
[null,null,"Physical Education Storage - Chiefland Elementary",null,30240,{"$nulls":5},30240]
[null,null,"Food Service - Joyce Bullock Elementary",null,1231120,{"$nulls":5},1231120]
[null,null,"Eight Primary Classrooms - Joyce Bullock Elementary",null,992497,{"$nulls":5},992497]
[null,null,"One Science Demonstration Room and Seven Classrooms - Williston Middle",null,905123,{"$nulls":5},905123]
[null,null,"Two Supplementary Instructional Classrooms - Williston Middle",{"$nulls":5},78210,null,78210]
[null,null,"Expand Food Service - Williston Middle",{"$nulls":5},359271,null,359271]
[null,null,"Remodel Locker and Dressing Area - Williston Middle",{"$nulls":6},81879,81879]
[null,null,"Expand Gym Locker and Dressing Rooms - Williston Middle",{"$nulls":6},115632,115632]
[null,null,"Four ESE Classroom Suites - Williston Middle School",{"$nulls":5},512820,null,512820]
[null,null,"Four Middle School Classrooms - Bronson High",null,437745,{"$nulls":5},437745]
[null,null,"Convert Two Classrooms to Science Demonstration - Bronson High",{"$nulls":6},80010,80010]
[null,null,"Renovate Science Labs 06-001, 10-001, and 10-021 - Chiefland High",{"$nulls":6},132006,132006]
[null,null,"Four Intermediate and Two Middle School Classrooms - Cedar Key",null,751719,{"$nulls":5},751719]
[null,null,"Expand Food Service - Yankeetown School",null,168000,{"$nulls":5},168000]
[null,null,"Construct Middle School Physical Education Facility - Yankeetown School",null,1186080,{"$nulls":5},1186080]
[null,null,"Four Intermediate, Two Middle School, and Two Primary Classrooms"]
[null,null,"Yankeetown School",null,999843,{"$nulls":5},999843]
[null,null,"Two ESE, Two Primary Classrooms, One ESE Resource Room, One "]
[null,null,"Elementary  Skills Lab and One Clinic - Yankeetown School",null,894432,{"$nulls":5},894432]
[null,null,"Renovate Building 04 - Yankeetown School",null,209664,{"$nulls":5},209664]
["5.",null,"LEVY Total",null,11606442,2846179,0,0,950301,971235,16374157]
[]
[]
["6 .",null,"Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[{"$nulls":4},"1998-99","1999-00","2000-01","2001-02","2002-03",null,"5 YEAR TOTAL"]
[null,null,"Effort Index Grants","None",0,0,0,0,0,null,0]
[null,null,"SIT Program awards received","None",0,0,0,0,0,null,0]
[null,null,"Other (specify)","None",0,0,0,0,0,null,0]
["6.",null,"LEVY Total",0,0,0,0,0,0,null,0]
[]
["7 .",null,"Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,null,"from current revenues projected over the next 5-years."]
[]
[null,null,"Project Description",null,"1998-99","1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR TOTAL"]
[null,null,"HVAC in Buildings 08 and 11 - Chiefland High School",{"$nulls":6},150000,150000]
[null,null,"Site Drainage - Cedar Key School",{"$nulls":6},50000,50000]
[null,null,"Convert Existing Media Center to Art and Music Suite - Joyce Bullock "]
[null,null,"Elementary",{"$nulls":6},207936,207936]
[null,null,"Renovate Building 01 and 02 - Joyce Bullock Elementary",{"$nulls":6},65000,65000]
[null,null,"Convert Building  01-07 and 01-33 to Vocational Lab - Chiefland Middle",{"$nulls":6},47089,47089]
[null,null,"Convert Building 01-009 to Music Suite - Chiefland Middle",{"$nulls":6},178850,178850]
[null,null,"Renovate Agriculture Building - Chiefland Middle",{"$nulls":6},80850,80850]
[null,null,"Renovate Lighting in Building 01 - Chiefland Middle",{"$nulls":6},165250,165250]
[null,null,"Convert Two Classrooms to Music - Bronson Elementary",{"$nulls":6},81600,81600]
[null,null,"Convert One Classroom to a Skills Lab - Bronson Elementary",{"$nulls":6},40800,40800]
[null,null,"Convert Room 7 Building 01 to Stage Dressing Room - Bronson High",{"$nulls":6},41265,41265]
[null,null,"Convert Room 11 Building 01 to Resource Room - Bronson High",{"$nulls":6},44289,44289]
[null,null,"Convert Three Classrooms to Administration - Bronson High",{"$nulls":6},120834,120834]
[null,null,"Convert Two Classrooms to Science Demonstration - Bronson High",{"$nulls":6},80010,80010]
[null,null,"Remodel Building 04 - Chiefland High",{"$nulls":6},343350,343350]
[null,null,"Convert Building 20 to Physical Education - Chiefland High",{"$nulls":6},183204,183204]
[null,null,"Renovate Building 03 - Chiefland High",{"$nulls":6},209832,209832]
[null,null,"Renovate Building 08 - Chiefland High",{"$nulls":6},769398,769398]
[null,null,"Renovate Building 11 - Chiefland High",{"$nulls":6},170478,170478]
[null,null,"Renovate Science Labs 06-001, 10-001, and 10-021 - Chiefland High",{"$nulls":6},132006,132006]
[null,null,"Remodel Building 04 - Williston High",{"$nulls":6},758835,758835]
[null,null,"Remodel Building 11 - Williston High",{"$nulls":6},87507,87507]
[null,null,"Build Playground - Bronson Elementary",{"$nulls":6},65000,65000]
[null,null,"Multi-Purpose Room and Chair Storage - Joyce Bullock Elementary",{"$nulls":6},326880,326880]
[null,null,"Stage Storage, Dressing, and Control Booth - Joyce Bullock Elementary",{"$nulls":6},203712,203712]
[null,null,"Custodial Storage - Joyce Bullock Elementary",{"$nulls":6},81600,81600]
[null,null,"Media Center - Joyce Bullock Elementary",{"$nulls":6},616032,616032]
[null,null,"ESE Classroom Suite - Williston Elementary",{"$nulls":6},124320,124320]
[null,null,"Construct Gymnasium - Chiefland Middle",{"$nulls":6},1701315,1701315]
[null,null,"Multi-Purpose Room and Chair Storage - Williston Middle",{"$nulls":6},271458,271458]
[null,null,"Remodel Locker and Dressing Area - Williston Middle",{"$nulls":6},81879,81879]
[null,null,"Stage and Adjoining Room - Williston Middle School",{"$nulls":6},190278,190278]
[null,null,"Band Classroom and Teacher Planning - Williston Middle ",{"$nulls":6},364815,364815]
[null,null,"ESE Special Vocational Lab - Williston Middle ",{"$nulls":6},132165,132165]
[null,null,"ESE Resource Room - Williston Middle ",{"$nulls":6},85833,85833]
[null,null,"Art Lab - Williston Middle ",{"$nulls":6},152559,152559]
[null,null,"Skills Development Lab and Teacher Planning - Williston Middle",{"$nulls":6},108009,108009]
[null,null,"Expand Gym Locker and Dressing Rooms - Williston Middle",{"$nulls":6},115632,115632]
[null,null,"Art Lab - Bronson High",{"$nulls":6},195707,195707]
[null,null,"Band Suite - Bronson High",{"$nulls":6},449580,449580]
[null,null,"Expand Agriculture Lab - Bronson High",{"$nulls":6},317500,317500]
[null,null,"New Parking Area - Bronson High",{"$nulls":6},55000,55000]
[null,null,"Two Resource Rooms - Cedar Key School",{"$nulls":6},112860,112860]
[null,null,"Supplementary Instructional Space - Cedar Key School",{"$nulls":6},30195,30195]
[null,null,"ESE Classroom - Cedar Key School",{"$nulls":6},128205,128205]
[null,null,"Convert Rooms 340,342,344,346, and 350 into a Guidance Office,"]
[null,null,"a Guidance Secretary's Office, an Itinerant Office, Textbook "]
[null,null,"Storage, Teacher Planning, Clinic, Computer Area, Career Room,"]
[null,null,"Conference Rooms, Storage Area, and Computer Lab"]
[null,null,"Williston High School",{"$nulls":6},367416,367416]
[null,null,"Warehouse - District Office",{"$nulls":6},750000,750000]
[null,null,"Transportation Work Bays - District Office",{"$nulls":6},60000,60000]
[null,null,"Bus Wash Area - District Office",{"$nulls":6},60000,60000]
[null,null,"Administrative Offices - District Office",{"$nulls":6},300000,300000]
[null,null,"Maintenance Offices, Conference, and Storage Shop Areas - District Office",{"$nulls":6},450000,450000]
["7.",null,"LEVY Total",null,0,0,0,0,0,11588833,11588833]
[]
[null,null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,null,"Project Description",null,"1998-99","1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR TOTAL"]
[null,null,"This row is for \"Checking and Balancing\" only",null,"Check Totals","Check Totals","","","Check Totals",null,"Check Totals"]
[]
["2.(b)",null,"To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,null,"education estimating conferences."]
[]
["(3)",null,"The adopted district facilities work program shall:"]
["(a)",null,"Be a complete, balanced capital outlay financial plan for the district."]
["(b)",null,"Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)",null,"The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,null,"funded in the program."]
{"$rows_empty":12}
["Respectfully submitted this ___________ day of ____________________, 1998."]
[]
[null,null,"SCHOOL BOARD OF ","LEVY  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:"]
[null,null,null,"Signature",null,null,"Name Printed",null,null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":10}," "]
[null,null,null,"Signature",null,null,"Name Printed",null,null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",{"$nulls":10}," "]
[{"$nulls":4},"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null,null," "]