{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["Recovered_Sheet1","01_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Recovered_Sheet1","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"01_5YrWkPlan","index":1,"n_rows":312,"n_cols":25,"rows_kept":312,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["WAKULLA  SCHOOL DISTRICT - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["WAKULLA   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted ",{"$nulls":8},"Last Revised",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format, as you received it (not a fax), prior to October 1, 2001, and all data accurate as of July 15, 2001.",{"$nulls":8},"2000-03-17",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"WAKULLA","Date: ==>","2001-10-01",null,"For fiscal years","  2001-2002 through 2005-2006"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[{"$nulls":8},0]
[{"$nulls":8},0]
[null,"Life Safety",{"$nulls":6},0]
[null,"Asbestos","Wakulla Hgh School",3390,{"$nulls":4},3390]
[{"$nulls":8},0]
[null,"HVAC Upgrades",{"$nulls":6},0]
[null,"Dehumidification","Medart",408000,{"$nulls":4},408000]
[null,"Chillers","Wakulla Middle School",152787,{"$nulls":4},152787]
[null,null,"Shadeville Elementaty"]
[null,"Hot Water Coils (Food Lab)","Wakulla High School ",10570]
[]
[null,"Furniture & Equipment","District Wide",81255.53,{"$nulls":4},81255.53]
[null,null,"Wakulla Middle School",47185.94,{"$nulls":4},47185.94]
[null,null,"Wakulla High School ",60688.2,{"$nulls":4},60688.2]
[null,"Roofing",{"$nulls":6},0]
[null,"Re-Roof","Crawfordville Elementary",236353,{"$nulls":4},236353]
[null,"Re-Roof","Wakulla High School ",75419]
[]
[{"$nulls":8},0]
[null,"P.E. Fields","Riversprings Middle School ",216366.97]
[null,null,"Wakulla Middle School ",57676.6]
[]
[null,"Test & Balance","Riverspring Middle School ",15615.4]
[]
[null,"District Office Renovation","Crawfordville Elementary School",null,null,2000000]
[]
[null,"Telephone System","Wakulla High School ",21979]
[null,null,"Wakulla Middle School",39560.74]
[null,null,"Wakulla Educational School ",11635.47]
[]
[null,"Intercom","Shadeville Elementary ",9600,{"$nulls":4},9600]
[]
[null,"EPA Fuel Tank Replacement","Bus Garage",null,null,null,100000,null,100000]
[{"$nulls":8},0]
[null,"Road Re-Surfacing","Medart",10002.7,{"$nulls":4},10002.7]
[null,null,"Wakulla Middle School",40348.39,{"$nulls":4},40348.39]
[]
[null,"P.E. LockerRenovations","Wakulla High School ",611176.55]
[]
[null,"Remodeling & Renovations","Wakulla High School",250000]
[]
[]
[]
[null,"Relocatables","District Wide",12602.5]
[]
[null,"Painting","District Wide",36833]
[]
[null,"Computers","District Wide",339732.12]
[]
[]
[]
[null,"Carpet","District Wide",76962.56,{"$nulls":4},76962.56]
[]
[]
[null,"Maintenance, Repair, and Renovation Totals",null,2825740.67,0,2000000,100000,0,1226573.3199999998]
[null," Less projected PECO Maintenance Funds (235.435(1))",null,256925,219817,202972,196708,197265,1073687]
["1.","WAKULLA Total",null,2568815.67,-219817,1797028,-96708,-197265,152886.31999999983]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"New Elem. School \"D\"",null,11333507,1259278,null,0,0,12592785]
[null,null,null,0,null,null,null,0,0]
[null,null,null,0,0,null,null,0,0]
[{"$nulls":6},0,0,0]
[null,null,null,0,0,null,null,null,0]
[null,null,null,0,0,0,null,null,0]
[null,null,null,0,0,0,0,null,0]
[null,null,null,0,0,null,0,0,0]
[null,null,null,0,0,0,null,0,0]
["2 .","WAKULLA Total",null,11333507,1259278,0,0,0,12592785]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"2000-01 FISH Satisfactory","Actual 2000-01","Actual 2000-01","Actual 2000-01","New Stu Capacity to","Projected 2005-06","Projected 2005-06"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"Medart",743,743,644,0.87,0,743,1]
[null,"Crawfordville",497,497,655,1.32,347,765,0.91]
[null,"Shadeville",806,806,693,0.86,0,806,1]
[null,"Wakulla Middle School",1086,997,643,0.64,0,569,0.57]
[null,"Riversprings",717,645,527,0.82,null,568,0.88]
[null,"Wakulla High School",1659,1576,1158,0.73,null,1275,0.81]
["2a.","WAKULLA Total",5508,5264,4320,0.82,347,4726,0.84]
[]
["2b.","Proposed Location of Planned Facilities"]
[null,"Replacement School For Crawfordville Elementary Located  1/4 mile to the west of existing School."]
[{"$nulls":6},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 2000-01","Owner","Student Stations","as classroom space","in 2005-06","units by 2005-06","Column \"C\""]
[null,"Crawfordville ",15,"WCSB",null,null,null,15]
[{"$nulls":7},0]
[{"$nulls":7},0]
[{"$nulls":7},0]
[{"$nulls":7},0]
[{"$nulls":7},0]
["2c1.","WAKULLA Total",15,null,0,0,0,15,"Avg Age 0"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06","5 YEAR TOTAL"]
[null,"Crawfordville",15,null,null,15,null,null,15]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2c2.","WAKULLA Total",15,0,0,15,0,0,15]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 2000-01","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2005-06","FISH Stu. Sta.","# Years Leased "]
[null,"Crawfrodville",2,"Williams/Sctsman",52,4,0,0,0]
[]
["2c3.","WAKULLA Total",2,null,52,4,0,0,0]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2005-06"]
[null,"St. Marks Elementaty/Middle",3,"Coast Charter School","1999-00",null,99,2,120]
[{"$nulls":8},0]
["2c4.","WAKULLA Total",3,null,null,0,99,2,99]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[]
[]
[]
[]
["2e.","Average Class Size (5 years out -- 2005-06) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","2000-01 CO-FTE","2000-01 Class size","2005-06 CO-FTE","be added (removed)","2005-06 Class size"]
[null,"Medart",28,743,644,23,743,null,26.54]
[null,"Shadeville",30,806,693,23.1,806,null,26.87]
[null,"Wakulla Middle School",30,997,643,21.43,569,null,18.97]
[null,"Riversprings",26,645,527,20.27,568,null,21.85]
[null,"Crawfordville",34,494,655,19,765,null,22.5]
[null,"Wakulla High School",59,1174,1158,19.63,1275,null,21.61]
["2e.","WAKULLA Total",207,4859,4320,"District Avg 21",4726,0,"District Avg 23"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,"Site                              ",null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06","5 YEAR AVERAGE"]
[null,"Crawfordville",null,345,345,0,0,0,138,null,79]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
["2f.","WAKULLA Total students in relocatables by year",null,345,345,0,0,0,138]
[null,"Total number of CO-FTE students projected by year",null,4381,4377,4423,4468,4601,4450]
[null,"Percent in relocatables by year",null,0.08,0.08,0,0,0,0.03]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"Replacement of Crawfordville School"]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",2000,2000,2000,2000,2000,2000]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,79,110,156,9213,12712,22844]
[null,"1999 State-wide totals - Gross Sq Ft per student station: Elem low 79, avg 110, high 156; Middle low 86, avg 113, high 165; High School low 68, avg 128, high 222 ",{"$nulls":7},2,86,113,165,9863,13571,18853]
[null,"1999 State-wide totals - Cost per student station: Elem low 9,213, avg 12,712, high 22,844; Middle low 9,863,avg 13,571, high 18,853; High School low 14,900, avg 18,106, high  26,448 ",{"$nulls":7},3,68,128,222,14900,18106,26448]
[]
["3a.","2001-02 Year","Type of School (new schools only)  Others=0","2001-02","2001-02 ","2001-02","2001-02","2000 State Avg","2000 State Avg","2000 State Avg","2000 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New Crawfordville School  ",1,10741000,844,114492,135.65,79,110,156,12726.3,9213,12712,22844]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3a.","WAKULLA Total 2001-02",null,10741000,844,114492,135.65,null,null,null,12726.3]
[]
["3b.","2002-2003 Year","Type of School (new schools only)  Others=0","2002-03 ","2002-03 ","2002-03 ","2002-03 ","2000 State Avg","2000 State Avg","2000 State Avg","2001 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3b","WAKULLA Total 2002-03",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3c.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","2000 State Avg","2000 State Avg","2000 State Avg","2002 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3c","WAKULLA Total 2003-04",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3d.","2004-2005 Year","Type of School (new schools only)  Others=0","2004-05","2004-05","2004-05","2004-05","2000 State Avg","2000 State Avg","2000 State Avg","2003 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3d.","WAKULLA Total 2004-05",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3e.","2005-2006 Year","Type of School (new schools only)  Others=0","2005-06","2005-06","2005-06","2005-06","2000 State Avg","2000 State Avg","2000 State Avg","2003 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3e","WAKULLA Total 2005-06",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3f.","WAKULLA 5-Year Total",null,10741000,844,114492]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,1053473,1275256,1466545,1686527,1939506,7421307]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,1053473,1275256,1466545,1686527,1939506,7421307,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",{"$nulls":6},0,0]
[null,"  less amount used to purchase other vehicles",{"$nulls":6},0,0]
[null,"  less amount transferred to operating budget for maintenance/repair",{"$nulls":6},0,0]
[null,"  less amount used for maintenance/repair",null,71038,126484,174306,1494197,1939506,3805531,0.51]
[null,"  less amount used to purchase capital outlay equipment",{"$nulls":6},0,0]
[null,"  less amount used to correct environmental problems",{"$nulls":6},0,0]
[null,"  less amount transferred to operating budget for salaries",{"$nulls":6},0,0]
[null,"  less amount used to pay debt service for s.237 loans",{"$nulls":6},0,0]
[null,"  less amount to pay debt service for COP's ",null,192330,192330,192330,192330,null,769320,0.1]
[null,"less amount to payback Special Facilities Account",null,790105,956442,1099909,null,null,2846456,0.38,"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,0,0,0,0,0,0,0,0]
[null,"P E C O New Construction",{"$nulls":4},62527,65464,127991,null,0.05]
[null,"C O & D S   Bond Proceeds  received on 20 March 1998",{"$nulls":6},0,null,0]
[null,"C O & D S maximum potential bond proceeds",null,238143,{"$nulls":4},238143,null,0.09]
[null,"Proceeds from 1/2 cent sales surtax authorized",{"$nulls":6},0,null,0]
[null,"Proceeds from a s.237 loan",{"$nulls":6},0,null,0]
[null,"Proceeds from local governmental infrastructure sales surtax",{"$nulls":6},0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",{"$nulls":6},0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",{"$nulls":6},0,null,0]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,1151423,473038,null,null,null,1624461,null,0.6]
[null,"Effort Index Grants",null,null,null,728322,null,null,728322]
[null,"Impact fees received",{"$nulls":6},0,null,0]
[null,"Private donations",{"$nulls":6},0,null,0]
[null,"Grants from local governments or not-for-profit organizations",{"$nulls":6},0,null,0]
["4.","WAKULLA Total",null,1389566,473038,728322,62527,65464,2718917,0.99,0.74]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
["5.","WAKULLA Total",0,0,0,0,0,0,0]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"SIT Program awards",null,0,0,0,0,0,0]
[null,"Other (specify)",null,0,0,0,0,0,0]
["6.","WAKULLA Total",null,0,0,0,0,0,0]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"New Crawfordville School",844,11333507,1259278,0,0,null,12592785]
[null,null,null,0,0,null,0,0,0]
[null,null,null,0,0,0,null,0,0]
["7.","WAKULLA Total",844,11333507,1259278,0,0,0,12592785]
[]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
["Respectfully submitted this ___________ day of ____________________, 2001."]
[]
[null,"SCHOOL BOARD OF ","WAKULLA  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:",{"$nulls":4},"David Miller",null,null,"2001-09-10"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":4},"Robert Myhre",null,null,"2001-09-10"," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",null,null,"William R. Bristol","Coordinator of Facilities","(850) 926-8111",null,"BristolR@wakulla.k12.fl.us",null," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}